## WakeDyn
Wake Dynamics
Objectives
1 | Significantly improve the physics-based understanding of wake flow dynamics and turbine interaction to enable the simulation and design of optimized wind plant
2 | Acquiring high-quality, high-resolution wind plant wake datasets suitable for the validation of wind turbine and wind plant high fidelity modeling tools
3 | Demonstrating V&V of computational modeling tools developed under the A2e initiative
4 | Developing new measurement instrumentation and methods as needed to support validation data requirements
Impacts
1 | Enhanced understanding of the wake development process within wind plants and its impact on the wind plant energy output, control, and reliability
2 | Validated, high-fidelity and engineering wind plant models disseminated for industrial use in wind plant design, optimization, and wake control
3 | Leveraging formal V&V principles from NNSA/NASA, use building block approach to improve fundamental understanding of turbine-to-turbine and array flow physics at different scales:
1) Intermediate Field Scale - leverage SWiFT facility with 2 or more 300kW turbines
2) Full Scale Field - turbines in utility scale wind plants
Tasks |  | 2018 Carryover | FY19 (BA & CO) | FY20 | FY21 | FY22 | FY23 | FY24 | FY25
1 | NRT Rotor Testing at SWiFT Facility
1.1 | NRT rotor set A: comissioning, characterization, and performance testing |  | 1269000 | 400000
1.2 | NRT rotor set B: manufacture, calibrate, commission, flight testing |  |  | 200000 | 150000
1.3 | Near-rotor Wake Dynamics Experimental Planning, Logistics and Safety |  |  | 900000 | 100000
1.4 | NRT rotor set C: Aero-instrumented blade set manufacture (2 aero-instrumented + 2 balanced structural instrumented), commissiong and flight testing |  |  | 600000 | 200000
1.5 | Near-Rotor Experiment Phase I: calibration |  |  |  | 400000 | 1700000 | 200000
1.6 | Near-Rotor Experiment Phase II: Validation data set |  |  |  |  | 200000 | 1330000 | 800000
1.7 | Near-Rotor Data Processing and archive | [5 empty] | 300000 | 900000 | 900000
| NREL: |  | 106000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
| SNL: |  | 1163000 | 2000000 | 750000 | 1800000 | 1730000 | 1600000 | 800000
| Task: 1.0 |  | 1269000 | 2100000 | 850000 | 1900000 | 1830000 | 1700000 | 900000
2 | Peetz Table Field Campaign
2.1 | Peetz Table Wake Testing: Complete wake steering and measurement campaign at Peetz Table wind farm |  | 1311000 | 1200000 | 400000
| NREL: |  | 1311000 | 1200000 | 400000
| Task: 2.0 |  | 1311000 | 1200000 | 400000 | 0 | 0 | 0 | 0
3 | AWAKEN Field Campaign
3.1 | AWAKEN planning: Finalize the science goals and select site for AWAKEN observation exepriment. Develop partnerships to increase international participation and create agreements for data sharing and site access. Encourage external funding in AWAKEN working with non-DOE funding agencies and writing proposals |  | 180000 | 400000 | 550000 | 500000
3.2 | AWAKEN Experiement Preparation: Identify critical instrumentation for AWAKEN to address science goals. Acquire instruments for testing. Simulate the test site and instrumentation and define optimal sensor placements. |  |  | 400000 | 1300000 | 1800000 | 2500000
3.3 | AWAKEN execution: Install instrumentation at site and calibrate prior to testing for long term and high fidelity testing. Execute field observations with long-term measurement systems. Execute field observations with high fidelity measurement systems. |  |  |  |  | 2000000 | 3900000 | 2900000
3.4 | Data archival and distribution |  |  |  |  | 200000 | 200000 | 200000
| NREL: |  | 100000 | 400000 | 950000 | 2400000 | 4000000 | 1700000
| SNL: |  | 80000 | 200000 | 500000 | 1500000 | 2000000 | 1000000
| LLNL: |  |  | 100000 | 200000 | 300000 | 300000 | 200000
| PNNL: |  |  | 100000 | 200000 | 300000 | 300000 | 200000
| Task: 3.0 |  | 180000 | 800000 | 1850000 | 4500000 | 6600000 | 3100000
4 | Flow Field, Load & Controls Validation Studies
4.1 | SWiFT validation studies: Wake steering, NRT, and Near-wake planning |  | 1328000 | 1200000 | 1200000
4.2 | SWiFT validation studies: Near-wake, blade loads and wake benchmark (IEA Task 29/31) |  |  |  |  | 800000 | 1200000 | 1000000 | 900000
4.3 | Peetz Table Valdiation Study: Using data gatherd from Peetz Table conduct multi-fidelity valdation study |  |  | 1200000 | 600000
4.4 | International Datasets valdiation studies: valdiation using data obtained through interational partnerships and IEA task 31 e.g. Lillgrund, Rodsand II |  | 684000 | 600000 | 600000 | 400000 | 400000 | 400000 | 400000
4.5 | AWAKEN valdiation studies (iterative with testing) and IEA Task 31 benchmarks |  |  |  | 800000 | 800000 | 1600000 | 1000000 | 400000
| NREL: |  | 864000 | 1400000 | 1600000 | 1000000 | 1600000 | 1200000 | 900000
| SNL: |  | 1148000 | 1600000 | 1600000 | 1000000 | 1600000 | 1200000 | 800000
| Task: 4.0 |  | 2012000 | 3000000 | 3200000 | 2000000 | 3200000 | 2400000 | 1700000
5 | Advanced Instrumenation development (proposed in AWAKEN MRP)
5.1 | Develop a roadmap for advanced microscale instrumenation development with external expert guidance. |  |  | 200000 | 100000
5.2 | Execute instrumentation development roadmap - simulate and test prototypes |  |  |  | 300000 | 800000 | 1000000 | 1000000
| NREL: |  |  | 50000 | 100000 | 300000 | 300000 | 300000
| SNL: |  |  | 50000 | 100000 | 300000 | 300000 | 300000
| LLNL: |  |  | 50000 | 100000 | 100000 | 200000 | 200000
| PNNL: |  |  | 50000 | 100000 | 100000 | 200000 | 200000
| Task: 5.0 |  |  | 200000 | 400000 | 800000 | 1000000 | 1000000
| Total Amount: |  | 4772000 | 7300000 | 6700000 | 9200000 | 12630000 | 8200000 | 2600000
Milestones & Deliverables |  |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25
1.1 | Baseline performance characterization of NRT rotor completed |  |  | Q2
1.2 | NRT aero-instrumented rotor manufactured |  |  |  | Q2
1.3 | Near-rotor experiment instrumentation plan completed |  |  |  | Q3
1.4 | NRT experimental aero-dynamic measurements compared to modeled predictions |  |  |  |  | Q3
1.5 | Near-rotor validation field experiment completed | [6 empty] | Q4
1.6 | Near-rotor validation data set QA/QC and archived for V&V application | [7 empty] | Q2
2.1 | Peetz Table Wind Farm measurement campaign complete |  |  | Q2
2.2 | Peetz Table Wind Farm data analysis complete and summary report |  |  |  | Q2
3.1 | Detailed AWAKEN Project Plan Completed |  |  | Q1
3.2 | AWAKEN site selection and contractual agreements commenced |  |  | Q4
3.3 | External AWAKEN funding proposals submitted |  |  |  | Q2
3.4 | Initial AWAKEN campaign design simulations and site layout complete |  |  |  | Q3
3.5 | AWAKEN Data sharing and land lease agreements complete |  |  |  | Q4
3.6 | AWAKEN field observation campaign commence |  |  |  |  | Q2
3.7 | Short term high resolution AWAKEN field campaign commence | [5 empty] | Q2
3.8 | AWAKEN field campaign completion | [5 empty] | Q4
3.9 | All AWAKEN project data and simulations results verified and uploaded to DAP | [6 empty] | Q2
3.1 | Final AWAKEN Project Report and Journal Publications | [6 empty] | Q4
4.1 | SWiFT wake steering benchmark final report |  |  | Q4
4.2 | Peetz Table validation study journal publication |  |  |  | Q3
4.3 | AWAKEN validation study journal publication and technical report | [6 empty] | Q3
5.1 | Publish Instrumentation development roadmap |  |  | Q2
5.2 | Release RFP for advanced microscale instrumentation |  |  |  | Q2
5.3 | Expert elicitation meeting on instrumentation development |  |  |  | Q1
5.4 | Demonstration of advanced microscale instrumentation capabilities |  |  |  |  | Q3

## ACOU
Aeroacoustics
Objectives
1 | Understand whether the implementation of active wind farm control adversely impacts wind plant aeroacoustic emissions and limits the viability and deployment of active control and increased AEP.
2 | If active wind plant control is determined to have significant aeroacoustic emissions impacting public acceptance and potential deployment, develop an R&D strategy to assess the underlying physics driving emissions and alternative mitigation strategies.
Impacts
1 | Understanding of whether acoustics emissions are incresased due to wind farm control strategies an resarch plan to address potential neagative impacts
2 | More efficiently operated plants without noise increases
Tasks |  | 2018 Carryover | FY19 (BA & CO) | FY20 | FY21 | FY22 | FY23 | FY24 | FY25
1 | Experimental Assessment of Turbine Level Noise and Propagation from Active Plant Control
1.1 | Experimental plan and instrumentation procurement |  | 250000
1.2 | Experimental execution |  |  | 300000
| NREL: |  | 250000 | 300000
| Task: 1.0 |  | 250000 | 300000
2 | Assessing Plant Level Noise and Propagation from Active Plant Control
2.1 | Complete noise model additions to OpenFAST |  | 100000
2.2 | Modeling of noise emissions and comparison to experiemental observations |  | 50000 | 150000
| NREL: |  | 150000 | 150000
| Task: 2.0 |  | 150000 | 150000
3 | Experimental Assessment of Acoustic Emission Measurement Technologies
3.1 | Asses adequacy of current noise measurement technology and cost plan for future development |  | 100000 | 50000
| NREL: |  | 100000 | 50000
| Task: 3.0 |  | 100000 | 50000
| Total Amount: |  | 500000 | 500000
Milestones & Deliverables |  |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25
1.1 | Initial testing plan for acoustic testing in conjunction with the wake steerting test |  | Q4
1.2 | Summary of acotuic test and summary of wake steering noise analysis |  |  | Q4
2.1 | Modeling summary fo wake steerign test and comparison to initial observations |  |  | Q2
3.1 | Summary of acoustic technology assesment and future development plan |  |  | Q1