## Sheet1
Aeroacoustics MYPP
Objectives
1 | Understand whether the implementation of active wind farm control adversely impacts wind plant aeroacoustic emissions and limits the viability and deployment of active control and increased AEP.
2 | If active wind plant control is determined to have significant aeroacoustic emissions impacting public acceptance and potential deployment, develop an R&D strategy to assess the underlying physics driving emissions and alternative mitigation strategies.
Impacts
1 | Understanding of whether acoustics emissions are incresased due to wind farm control strategies an resarch plan to address potential neagative impacts
2 | More efficiently operated plants without noise increases
Tasks |  | 2018 Carryover | FY19 (BA & CO) | FY20
1 | Experimental Assessment of Turbine Level Noise and Propagation from Active Plant Control
1.1 | Experimental plan and instrumentation procurement |  | 250000
1.2 | Experimental execution |  |  | 300000
| NREL: |  | 250000 | 300000
| Task: 1.0 |  | 250000 | 300000
2 | Assessing Plant Level Noise and Propagation from Active Plant Control
2.1 | Complete noise model additions to OpenFAST |  | 100000
2.2 | Modeling of noise emissions and comparison to experiemental observations |  | 50000 | 150000
| NREL: |  | 150000 | 150000
| Task: 2.0 |  | 150000 | 150000
3 | Experimental Assessment of Acoustic Emission Measurement Technologies
3.1 | Asses adequacy of current noise measurement technology and cost plan for future development |  | 100000 | 50000
| NREL: |  | 100000 | 50000
| Task: 3.0 |  | 100000 | 50000
| Total Amount: |  | 500000 | 500000 | <- Looks like this might be only carryover from FY19 (~$378k)
Milestones & Deliverables |  |  | FY19 | FY20
1.1 | Initial testing plan for acoustic testing in conjunction with the wake steerting test |  | Q4
1.2 | Summary of acotuic test and summary of wake steering noise analysis |  |  | Q4
2.1 | Modeling summary fo wake steerign test and comparison to initial observations |  |  | Q2
3.1 | Summary of acoustic technology assesment and future development plan |  |  | Q1