## Slide 1: NREL Wind – 1.3 - Atmosphere to Electrons (A2e) FY19 Q4 Project Status Overview
Project | Financial Status | Schedule/ Milestones
1.3.1.401 - A2e: Measurement, Testing, and Verification (WFIP Support)* |  | 
1.3.1.402 - WFIP II Extended Analysis |  | 
1.3.2.401 - MMC - Model Development & Validation* |  | Category: Lab - Technical Delay
1.3.3.401 - High-Fidelity Modeling* |  | Category: Lab - Technical Delay
1.3.3.402 - Energy Research and Forecast Modeling | Category: Lab - External Project Partner | No milestones in FY19
1.3.4.401 - Rotor Wake Measurements & Predictions for Validation* |  | 
1.3.4.403 – Aeroacoustic Assessment of Wind Plant Control | Category: Lab – Procurement/Acquisition Delay | 
1.3.4.404 American Wake Experiment (AWAKEN) | Category: Lab - Project or Budget Planning | No Milestones in FY19.``
1.3.5.401 - Advanced Flow Control Science for Wind Plants |  | 
1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control | No costing planned in FY19. | No milestones in FY19
1.3.6.401 - Systems Engineering & Optimization |  | 
1.3.6.402 - Multi Physics Model Validation & UQ | Category: (1) Lab – Project or Budget Planning; (2) Lab - External Project Partner | Category: Lab – Project or Budget Planning
1.3.6.403 - Modeling and Validation for Offshore Wind |  | Category: Lab - External Project Partner
1.1.3.9.401 - A2e EMC Support | Lab - Project or Budget Planning | No milestones required.
  1.3.2.401 (PNNL – Designated Reporting Lab)
  1.3.4.401 (NREL – Designated Reporting Lab)
** Slides included separately as a Multi-Lab Project Report:
  1.3.1.401 (PNNL – Designated Reporting Lab)
  1.3.3.401 (NREL) – Designated Reporting Lab)
Notes: There should only be ONE WBS overview slide per WBS Deck, summarizing the WBS Status stoplights that appear on slide 1 of each 3-slide subdeck.

## Slide 2: NREL Wind – 1.3.1.401 - A2e: Measurement, Testing, and Verification (WFIP Support) Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 3: NREL Wind – 1.3.1.401 - A2e: Measurement, Testing, and Verification (WFIP Support) FY19 Q4 Project Overview
Project Attributes
Budget
Total: $265,152 (2019 AOP Guidance: $0, Carryover: $50,152)
Project PI
Caroline Draxl caroline.draxl@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Project Summary
ANL, NREL, & PNNL Project is closed. Additional work will be done under WFIP2 extension. LLNL Continue to gather atmospheric measurements of wind using three lidars at Site 300 along three ridgelines (field experiment called HilFlowS). Retrieve and rebuild the solar panel/battery skid which is currently at NNSS. This will allow deployment of one lidar in the valley at Site 300 between two instrumented ridgelines for a hill-valley-hill dataset. Summer student will present her WFIP2 related work at the LLNL summer student poster symposium in August. Deliver HilFlowS wind lidar measurements to WFIP2 team to study transferability of model improvements by the end of the FY. Contribute to revisions of submitted papers as needed. Continue preparation of manuscript on the development of a new immersed boundary method for intermediate resolutions.
Project Objective & Impact

## Slide 4: NREL Wind – 1.3.1.401 - A2e: Measurement, Testing, and Verification (WFIP Support) FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project complete.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | Project complete.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 5: NREL Wind - 1.3.1.401 - A2e: Measurement, Testing, and Verification (WFIP Support) FY19 Q4 Project Financial Status
Total: $265,152 (2019 AOP Guidance: $0, Carryover: $50,152)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 50152 | 15869 | 5480 | 408 | 390
Total Funding Level (Cum.) | 265152 | 265152 | 265152 | 50152 | 50152
FY19 Funding Received (Cum.) | 50152 | 50152 | 50152 | 50152 | 50152
Projected Recipient Spend Plan (Cum.) | 0 | 40016 | 50152 | 50152 | 50152
Actual Accrued or Invoiced Costs (Cum.) | 0 | 34191 | 44580 | 49652 | 49670
Actuals + Commitments (Cum) | 0 | 34283 | 44672 | 49744 | 49762
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 6: NREL Wind – 1.3.1.401 - A2e: Measurement, Testing, and Verification (WFIP Support) FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
1.3.1.401 Q1: By 12/31/2018 perform a literature review of state-of-the-art in machine learning applied to wind power forecasting (includes industry engagement). (Quarterly Progress Measure (Regular)) | 100% | 12/31/2018
1.3.1.401 Q2: By 3/31/19 prepare a report on best performing statistical models (both algorithm and atmospheric input features) for application to Columbia Gorge wind farms (analysis based on measured atmospheric data). (Quarterly Progress Measure (Regular)) |  | 
1.3.1.401 Q3: By 6/30/2019 prepare a report to document the model improvements on one atmospheric phenomenon (mountain wave or cold pool) and the impact of those on a wind farm in the Columbia River Gorge. (Quarterly Progress Measure (Regular)) |  | 
1.3.1.401 Q4: By 9/30/19 prepare a report on best performing statistical models for converting HRRR forecasts into power forecasts in the Columbia River Gorge. (Annual Milestone (Regular)) |  | 

## Slide 7: NREL Wind – 1.3.1.401 - A2e: Measurement, Testing, and Verification (WFIP Support) FY19 Q4 Project Milestone Status
Work accomplished this quarter: Public Outreach/Industry Engagement:
90-Day Outlook: See 1.3.1.402 - WFIP II Extended Analysis Upcoming Public Outreach/Industry Engagement:

## Slide 8: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 9: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY19 Q4 Project Overview
Project Attributes
Budget
Total: $215,000 (Carryover: $0, 2019 Budget Authority: $215,000)
Project PI
Caroline Draxl caroline.draxl@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Caroline Draxl
Project Summary
Through WFIP2, significant forecast improvements were made by improving how numerical weather predictions (NWP) model treat complex terrain, vertical mixing between the surface and the upper atmosphere, and the impact of turbulence in the horizontal as well as vertical. Several of these have been included in the recent release of NOAA's current operational weather forecast model. However, there are other known significant sources of turbine-height forecast error that were beyond the scope of the planned WFIP2 analysis, such as errors arising within the NWP models from the land-surface models (LSMs) and the treatment of clouds. These sources of error can be addressed with additional simulations and by making use of the extensive data set collected during WFIP2.
Project Objective & Impact
The WFIP 2 dataset is a unique resource in complex terrain owing both to the extent of observations over many atmospheric scales and more than a full year of continuous measurements. We propose to use this dataset in new and expanded analyses to improve forecast accuracy through developing additional improvements to the model physics and wind power forecasting techniques. New analyses will focus on improving the LSM and cloud parameterizations in the forecast models. Additional development will build on WFIP2 progress in mathematically describing horizontal variability of turbulence and improved numerical treatment of complex topography. Methods of uncertainty quantification will be used to understand key model sensitivities to LSM and cloud parameters as well as to define overall uncertainties in improved model forecasts. Knowledge gained will be transferred, in collaboration with NOAA, to the National Weather Service’s foundational weather forecast models. Overall Project Goals and Objectives ● Evaluation and improvement of the representation of boundary-layer turbulence and surface energy exchange ● Improved understanding of model treatment of clouds on turbine-level winds ● Further improvements to model representations of horizontal variability ● Quantification of model uncertainties and application of formal verification and validation methods to model improvements

## Slide 10: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 11: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $215,000; FY19 Beginning Uncosteds: $0)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 0 | 0 | 0 | 135105 | 133655
Total Funding Level (Cum.) | 0 | 0 | 0 | 215000 | 215000
FY19 Funding Received (Cum.) | 0 | 0 | 0 | 161250 | 215000
Projected Recipient Spend Plan (Cum.) | 0 | 0 | 0 | 30639 | 77186
Actual Accrued or Invoiced Costs (Cum.) | 0 | 0 | 0 | 26145 | 81345
Actuals + Commitments (Cum) | 0 | 0 | 0 | 26145 | 81345
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 12: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
NREL FY19 Q3: Draft report about the impact of mountain waves on wind farm power output. (Quarterly Progress Measure (Regular)) | 100% | 6/27/2019
NREL FY19 Q4 Annual (SMART) Milestone: Deliver a joint report to DOE describing collaborative progress with other labs in FY19. (Annual Milestone (Regular)) This milestone modified per AOP mod approved in Q4. | 100% | 9/30/2019

## Slide 13: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY19 Q4 Project Milestone Status
Work accomplished this quarter: NREL Modification of flow model FLORIS to calculate power output in complex terrain. Evaluating Lidar performance in complex terrain Work towards a journal publication of “Mountain waves impact wind energy” Participation in IEA Wind Task 36: joining regular meetings, review documents Delivered a joint report to DOE describing collaborative progress with other labs in FY19 Presentation about mountain waves in complex terrain and their impact on wind energy at the International Conference on Alpine Meteorology in Riva, Italy. Public Outreach/Industry Engagement:
90-Day Outlook: NREL Selection of a case study to validate improvements in the HRRR. Work towards a journal publication of “Mountain waves impact wind energy” Work towards Q4 milestone report documenting the impact of Land Surface Models (LSM) on hub-height winds, including recommendations for improvements to the LSM and surface layer schemes. Invited talk at AGU in San Francisco in December, which will include an overview of WFIP 2 Upcoming Public Outreach/Industry Engagement:

## Slide 14: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 15: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation FY19 Q4 Project Overview
Project Attributes
Budget
Total: $781,069 (Carryover: $381,069, 2019 Budget Authority: $400,000)
Project PI
Overall PI: Sue Haupt (NCAR) haupt@ucar.edu 303-497-2763 NREL PI: Matt Churchfield matt.churchfield@nrel.gov 303-702-0890
DOE Lead
Mike Derby Michael.Derby@ee.doe.gov 202-586-6830
Key Personnel
Project Summary
Coupling mesoscale (grid spacing on the order of kilometers) and microscale (grid spacing on the order of meters to tens of meters) models is an important step forward for the wind power industry. New techniques and tools are needed to better understand the turbulent flow into and within the wind plant, which impacts energy transfer between scales, and ultimately, the amount of power. The ability to couple these scales is particularly important for non-stationary meteorological conditions (such as frontal passages, thunderstorm outflows, baroclinic systems, and low-level jets) or when considering changes of atmospheric stability associated with the diurnal cycle.
Project Objective & Impact
Apply verification and validation (V&V) techniques to the new modeling tools that are developed to ensure the accuracy of our codes and results and develop estimates of the uncertainty Improve computational performance of the coupled MMC models through the development of methods that can be used to reduce turbulence spin-up time and hence the size of computational domains Improve representation of the surface layer in microscale models to improve simulations of wind speed and shear over the rotor diameter Develop guidance for the community describing the best ways to couple mesoscale and microscale models, including specific spatial scales at which the handoff to the microscale model should occur Prepare documentation and a suite of software tools that can be used across the community Transition MMC research to the offshore environment.

## Slide 16: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 17: NREL Wind - 1.3.2.401 - MMC - Model Development & Validation FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $400,000; FY19 Beginning Uncosteds: $381,069)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 381069 | 276897 | 249894 | 152483 | 141335
Total Funding Level (Cum.) | 781069 | 781069 | 781069 | 781069 | 781069
FY19 Funding Received (Cum.) | 381069 | 460762 | 581067 | 681069 | 781069
Projected Recipient Spend Plan (Cum.) | 0 | 172298 | 318845 | 478013 | 622567
Actual Accrued or Invoiced Costs (Cum.) | 0 | 183865 | 328461 | 528586 | 639734
Actuals + Commitments (Cum) | 0 | 183865 | 331173 | 528586 | 639734
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 18: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: By December 31, 2018, NREL will provide an assessment of the “mesoscale-profile assimilation” technique in the form of a short report. This technique was developed earlier, and it is a means to force the microscale mean profiles to match any given profile, either from mesoscale simulations or observations, but it has not been thoroughly tested under different conditions. (Quarterly Progress Measure (Regular)) | 100% | 12/31/2018
Q2: By March 31, 2019, NREL will provide an assessment of the mesoscale-to-microscale interface requirements in complex terrain. Specifically, the distance upstream of the location of interest, the blending of coarse resolution mesoscale to fine resolution microscale terrain, and the requirement for inflow turbulence perturbations will be addressed, all as a function of terrain complexity. (Quarterly Progress Measure (Regular)) | 100% | 3/31/2019
Q3: By June 30, 2019, NREL will provide a comparison between LES-generated turbulent inflow and synthetic turbulence or cell-perturbation-based turbulence in a complex terrain site, such as Biglow Canyon or the NWTC. This turbulence is applied at the mesoscale-microscale interface to accelerate the formation of realistic turbulence within the microscale domain. (Quarterly Progress Measure (Regular)) |  | 
Q4: By September 30, 2019, NREL will build upon their FY18Q1 report on wind-plant-centric quantities of interest and validation techniques for mesoscale-microscale coupling around wind plants. (Annual Milestone (Regular)) |  | 

## Slide 19: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation FY19 Q4 Project Milestone Status
Work accomplished this quarter: Public Outreach/Industry Engagement:
90-Day Outlook: Upcoming Public Outreach/Industry Engagement:

## Slide 20: NREL Wind – 1.3.3.401 - High-Fidelity Modeling Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 21: NREL Wind – 1.3.3.401 - High-Fidelity Modeling FY19 Q4 Project Overview
Project Attributes
Budget
Total: $1,918,999 (Carryover: $444,917, 2019 Budget Authority: $1,474,082)
Project PI
Michael Sprague michael.a.sprague@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Project Summary
Summarize from AOP
Project Objective & Impact
Summarize from AOP

## Slide 22: NREL Wind – 1.3.3.401 - High-Fidelity Modeling FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab - Technical Delay

## Slide 23: NREL Wind - 1.3.3.401 - High-Fidelity Modeling FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $1,474,082; FY19 Beginning Uncosteds: $444,917)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 444917 | 402123 | 497635 | 475391 | 354356
Total Funding Level (Cum.) | 1918999 | 1918999 | 1918999 | 1918999 | 1918999
FY19 Funding Received (Cum.) | 444917 | 738554 | 1181957 | 1550479 | 1918999
Projected Recipient Spend Plan (Cum.) | 0 | 352550 | 684926 | 1103426 | 1498649
Actual Accrued or Invoiced Costs (Cum.) | 0 | 324687 | 639338 | 1068698 | 1537486
Actuals + Commitments (Cum) | 0 | 336431 | 684322 | 1075088 | 1564643
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 24: NREL Wind – 1.3.3.401 - High-Fidelity Modeling FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
FY19Q1 (NREL/SNL): Assemble a working group of external and internal HFM stakeholders to define comparison criteria for benchmarking public-domain wind HFM simulation codes. Future open benchmarking will be conducted in accordance with the predictive-simulation goals described in the 2015 technical report “A2e High Fidelity Modeling: Strategic Planning Meetings.”. (Quarterly Progress Measure (Regular)) | 100% | 12/31/2018
FY19Q2 (NREL/SNL): Go/No-Go: Demonstrate the ability of the Nalu-Wind computational framework to produce statistically meaningful results for unsteady Reynolds-Averaged-Navier-Stokes (URANS) simulations with the large time-step sizes that will be required in fully resolved wind turbine simulations. (Quarterly Progress Measure (Regular)) | 100% | 3/30/2019
FY19Q2 (NREL/SNL): Go/No-Go: Demonstrate the ability of the Nalu-Wind computational framework to produce statistically meaningful results for unsteady Reynolds-Averaged-Navier-Stokes (URANS) simulations with the large time-step sizes that will be required in fully resolved wind turbine simulations. (Go/No-Go) | 100% | 3/31/2019
FY19Q3 (NREL/SNL): Provide DOE-WETO an internal assessment of resources and timelines required to achieve (1) parity with SOWFA actuator-line capability currently available to industry, and (2) achieve full fluid-structure-interaction resolution of a single turbine over statistically meaningful time durations. (Quarterly Progress Measure (Regular)) |  | 
FY19Q4 (NREL/SNL-Annual): Execute the first annual benchmarking event as defined in the Q1 milestone, and exercise the relevant Nalu-Wind/OpenFAST capabilities. (Annual Milestone (Regular)) |  | 

## Slide 25: NREL Wind – 1.3.3.401 - High-Fidelity Modeling FY19 Q4 Project Milestone Status
Work accomplished this quarter: Highlight major work accomplishments (please add another slide to the deck if you need extra space for this description) Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content)
90-Day Outlook: Anticipated work for next quarter (please add another slide to the deck if you need extra space for this description) Upcoming Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content, etc.)

## Slide 26: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 27: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling FY19 Q4 Project Overview
Project Attributes
Budget
Total: $31,250 (Carryover: $0, 2019 Budget Authority: $31,250)
Project PI
Eliot Quon eliot.quon@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Project Summary
Many wind energy developments are plagued by underperformance and reliability issues, due to inadequacy of physics and computational capabilities within existing simulation codes. The Energy Research and Forecasting (ERF) will be a next-generation fluid dynamics simulation code targeting larger scales of atmospheric flows, capable of providing accurate meteorological and environmental forcings for high-fidelity models of the wind plant environment.
Project Objective & Impact
ERF will improve upon the established Weather Research and Forecasting (WRF) model, optimizing the code for modern HPC infrastructures and enhancing parallel scalability. This will permit more efficient simulation of larger nested domains with higher resolution. ERF will eliminate simulation bottlenecks that were in WRF, such as initialization and file I/O, and address the shortcomings of WRF’s load balancing and downscaling algorithms, numerical methods, and physics parameterizations. ERF will enable seamless coupling with microscale solvers such as Nalu-Wind by implementing physics modules and algorithms developed in the WETO Mesoscale-to-Microscale Coupling project, thereby facilitating high-fidelity multiscale wind plant simulations.

## Slide 28: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 64% underspent. The lead lab was delayed in initiating project. The kick-off meeting and workshop, and associated tasks, have been pushed to FY20 Q1.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab - External Project Partner
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 29: NREL Wind - 1.3.3.402 - Energy Research and Forecast Modeling FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $31,250; FY19 Beginning Uncosteds: $0)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 0 | 0 | 0 | 0 | 22209
Total Funding Level (Cum.) | 0 | 0 | 0 | 31250 | 31250
FY19 Funding Received (Cum.) | 0 | #N/A | #N/A | #N/A | 31250
Projected Recipient Spend Plan (Cum.) | 0 | 0 | 0 | 0 | 25077
Actual Accrued or Invoiced Costs (Cum.) | 0 | 0 | 0 | 0 | 9041
Actuals + Commitments (Cum) | 0 | 0 | 0 | 0 | 9041
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 30: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
No Milestones in FY19. |  | 

## Slide 31: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling FY19 Q4 Project Milestone Status
Work accomplished this quarter: A code development repository on GitHub has been established, tracking release version 4.1.2 of the Weather Research and Forecasting Model. Public Outreach/Industry Engagement:
90-Day Outlook: Meet with NREL researchers to establish relationship between ERF and the existing High-Fidelity Modeling (HFM) project. Plan meeting agenda for upcoming kick-off meeting and workshop, set for Oct 30-31, 2019. Together with ANL, LLNL, and PNNL, summarize workshop proceedings and short-term/long-term code development plans in a report. Establish repository access protocols and standards for ERF code development. Develop plan for software quality assurance, based on past experiences with HFM. This plan will include identification of hardware requirements and strategies for software testing given different hardware and high-performance computing resource availability scenarios. Upcoming Public Outreach/Industry Engagement:

## Slide 32: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 33: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY19 Q4 Project Overview
Project Attributes
Budget
Total: $3,493,439 (Carryover: $1,185,619, 2019 Budget Authority: $2,307,820)
Project PI
Patrick Moriarty patrick.moriarty@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Project Summary
Summarize from AOP
Project Objective & Impact
Summarize from AOP

## Slide 34: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 35: NREL Wind - 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $2,307,820; FY19 Beginning Uncosteds: $1,185,619)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 1185619 | 597804 | 444226 | 445189 | 510933
Total Funding Level (Cum.) | 3260619 | 3260619 | 3260619 | 3260619 | 3493439
FY19 Funding Received (Cum.) | 1185619 | 1599031 | 2223121 | 2741869 | 3493439
Projected Recipient Spend Plan (Cum.) | 0 | 694738 | 1566295 | 2107488 | 2969607
Actual Accrued or Invoiced Costs (Cum.) | 0 | 763671 | 1586070 | 2133773 | 2786224
Actuals + Commitments (Cum) | 0 | 1001227 | 1778895 | 2296680 | 2982506
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 36: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
1.3.4.401, Q1: Submit a journal article which analyzes the results to date of the wake steering experiment at NetEra Peetz table wind farm that will demonstrate the observed value of wind farm control at full scale. (Quarterly Progress Measure (Regular)) | 100% | 12/31/2018
1.3.4.401, Q2: Present validation study of NREL developed wind farm simulation tools using full-scale operational wind farm data at AIAA SciTech Meeting, January 7, 2019. (Quarterly Progress Measure (Regular)) | 100% | 3/31/2019
1.3.4.401, Q3: IEA Task 31 WakeBench presentation on summary of the international validation comparison study of the SWiFT Case at Visby Wake Conference May 22, 2019 (Joint with SNL). (Annual Milestone (Regular)) |  | 
1.3.4.401, Q4: Submit journal publication focused on validation study and demonstrating validation process using at least one data set from Wake Dynamics project analysis. (Quarterly Progress Measure (Regular)) |  | 

## Slide 37: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY19 Q4 Project Milestone Status
Work accomplished this quarter: Highlight major work accomplishments (please add another slide to the deck if you need extra space for this description) Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content)
90-Day Outlook: Anticipated work for next quarter (please add another slide to the deck if you need extra space for this description) Upcoming Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content, etc.)

## Slide 38: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 39: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY19 Q4 Project Overview
Project Attributes
Budget
Total: $500,000 (Carryover: $0, 2019 Budget Authority: $500,000)
Project PI
Nicholas Hamilton nicholas.hamilton@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Nicholas Hamilton
Project Summary
The extent to which modern wind plant control strategies induce additional aeroacoustic emissions from additional separation and other flow interaction dynamic effects is not known, and may have a significant impact on future wind plant development and wind turbine siting. Off-nominal rotor control by prescribed yaw misalignment is expected to induce periodic flow separation locally along the rotor blades and change the aerodynamic interaction with the local flow field. Given public concerns about wind turbine noise and the need for observational data required for regulators to establish noise restrictions, potential acoustic emissions resulting from active control must be understood prior to commercial deployment and the development of practical noise reduction methods and technology. Additional downstream acoustic propagation effects introduced by active yaw and or thrust control must be investigated and understood for modern wind plant control strategies to be successfully implemented at the utility scale.
Project Objective & Impact
Aeroacoustics project objectives are focused on quantifying the additional acoustic emissions introduced by implementing modern wind turbine and wind plant control strategies. Acoustic noise produced by wind turbines is one of the limiting factors on their operation and one of the constraints placed on development of wind plants. Specific FY19 and FY20 objectives are to: Experimentally quantify the aeroacoustic emissions of a utility scale wind turbine operating under yawed conditions. Determine the nature of the changes to the overall sound pressure level directivity under the influence of yaw misalignment. Update and validate aeroacoustic modeling software to integrate into current OpenFAST framework against observational data collected experimentally. Disseminate findings of aeroacoustic field observations for a utility-scale wind turbine operating under prescribed yaw offsets though peer-reviewed journal publications

## Slide 40: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 51% underspent. Project is underspent due to a delay in the acquisition of instrumentation and equipment required to execute the experimental test plan. It was determined that the test plan should be fully developed before instruments were purchased to ensure that the project goals could be met effectively and that instrumentation would continue to add value to NREL activities in coming years. Instrumentation acquisition has been delayed until FY20 Q1.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab – Procurement/Acquisition Delay
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 41: NREL Wind - 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $500,000; FY19 Beginning Uncosteds: $0)
Subcontracts/Commitments: Acoustic instrumentation will be acquired to make experimental observations in support of the project goals and milestones. FY19 spending on instrumentation (originally estimated at $40k) has been delayed to ensure that the correct instrumentation is acquired. FY19 and FY20 funds will be combined to acquire all necessary equipment in FY20 Q1, totaling $90k. Suppliers include Brüel & Kjær (for microphones, preamplifiers, signal conditioners, ~$60k), National Instruments (for data acquisition platform ~$12k), Delta (for data processing software ~$6k), cabling/microphone soundboards/hardware (~$10k)
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 0 | 0 | 0 | 375000 | 445743
Total Funding Level (Cum.) | 0 | 0 | 0 | 500000 | 500000
FY19 Funding Received (Cum.) | 0 | #N/A | #N/A | 375000 | 500000
Projected Recipient Spend Plan (Cum.) | 0 | 0 | 0 | 0 | 111483
Actual Accrued or Invoiced Costs (Cum.) | 0 | #N/A | #N/A | 0 | 54257
Actuals + Commitments (Cum) | 0 | #N/A | #N/A | 0 | 54257
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 42: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
1.3.4.403 - FY19Q4: NREL will complete a detailed plan for aeroacoustic measurements of a utility scale wind turbine operating under conditions specified in modern wind plant control strategies by September 30, 2019. | 100% | 9/30/19

## Slide 43: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY19 Q4 Project Milestone Status
Work accomplished this quarter: Project officially started in FY19 Q4, including: development of an AOP, interaction with DOE coordinator, scoping objectives and milestones for the near term and for the extent of the project and forming the project team. Completed test plan to collect aeroacoustic observations around the the DOE 1.5 MW turbine at NREL Flatirons including sensor placement, yaw and turbine operation schedule, and key individuals for coordination of activities at Flatirons. Public Outreach/Industry Engagement: Industry engagement for the aeroacoustics assessment project has been limited to inquiries to instrumentation and equipment suppliers. Contact has been made with wind turbine acoustics experts at Technical University of Munich (TUM), University of Stuttgart (US), and the Danish Technical University (DTU) to ensure that the planned study will be of scientific relevance to the relevant research community.
90-Day Outlook: FY20 Q1 will be focused on specifying instrumentation and equipment needs to support the test plan developed in FY19 Q4. The detailed schedule for observations will be refined as instrumentation is brought on board, calibrated and tested on site. Any modifications to the test plan as required by outside constraints (sensor placement, site access, coordination with other research) will be factored into and incorporated into the working test plan document. Upcoming Public Outreach/Industry Engagement: Continued engagement with the wind turbine aeroacoustics research community will inform instrument specification and acquisition and avoid pitfalls in data collection and processing. No public dissemination of test results is planned for the aeroacoustics project until FY20 Q3.

## Slide 44: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 45: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) FY19 Q4 Project Overview
Project Attributes
Budget
Total: $250,000 (Carryover: $0, 2019 Budget Authority: $250,000)
Project PI
Patrick Moriarty patrick.moriarty@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Project Summary
Summarize from AOP
Project Objective & Impact
Summarize from AOP

## Slide 46: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 32% underspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab - Project or Budget Planning
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 47: NREL Wind - 1.3.4.404 - American Wake Experiment (AWAKEN) FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $250,000; FY19 Beginning Uncosteds: $0)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 0 | 0 | 0 | 187500 | 175344
Total Funding Level (Cum.) | 0 | 0 | 0 | 250000 | 250000
FY19 Funding Received (Cum.) | 0 | #N/A | #N/A | 187500 | 250000
Projected Recipient Spend Plan (Cum.) | 0 | 0 | 0 | 0 | 110372
Actual Accrued or Invoiced Costs (Cum.) | 0 | #N/A | #N/A | 0 | 74656
Actuals + Commitments (Cum) | 0 | #N/A | #N/A | 0 | 74656
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 48: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
No Milestones in FY19. |  | 

## Slide 49: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) FY19 Q4 Project Milestone Status
Work accomplished this quarter: Highlight major work accomplishments (please add another slide to the deck if you need extra space for this description) Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content)
90-Day Outlook: Anticipated work for next quarter (please add another slide to the deck if you need extra space for this description) Upcoming Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content, etc.)

## Slide 50: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 51: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY19 Q4 Project Overview
Project Attributes
Budget
Total: $1,697,214 (Carryover: $597,214, 2019 Budget Authority: $1,100,000)
Project PI
Paul Fleming Paul.fleming@nrel.gov 303-384-6918
DOE Lead
Mike Derby Michael.Derby@ee.doe.gov
Key Personnel
Paul Fleming Jennifer King Alan Wright Eric Simley Christopher Bay
Project Summary
A smart plant, where the control activities of individual turbines are coordinated by a central wind farm controller, using information from each of the turbines as well as additional available sensing such as lidars, can substantially improve the performance of existing and new wind farms. Advanced flow control science for wind plants research provides the implementation strategies and methods to deliver wind plant performance improvements.
Project Objective & Impact
This project will develop the technical capabilities, methods, and approaches that enable “smart plant” control design to optimize wind plants with respect to energy capture and loads. The project will advance wind farm control-oriented modeling to include advanced vortex physics, wake interaction and energy entrainment, as well as the impact of atmospheric stability. The project will deliver new wind farm control strategies and algorithms that can manipulate underlying physical phenomenon driving performance. The project will perform field campaign and LES-based evaluation of control model and strategy effectiveness and performance. Finally it will provide a complete control model and generic strategy for implementing and evaluating strategies for offshore floating platforms.

## Slide 52: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 53: NREL Wind - 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $1,100,000; FY19 Beginning Uncosteds: $597,214)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 597214 | 378075 | 333449 | 225797 | 398245
Total Funding Level (Cum.) | 1497214 | 1497214 | 1497214 | 1497214 | 1697214
FY19 Funding Received (Cum.) | 597214 | 776525 | 1047214 | 1272214 | 1697214
Projected Recipient Spend Plan (Cum.) | 0 | 306541 | 584113 | 910427 | 1300058
Actual Accrued or Invoiced Costs (Cum.) | 0 | 275972 | 636269 | 1007669 | 1279039
Actuals + Commitments (Cum) | 0 | 398450 | 713765 | 1046417 | 1298969
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 54: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
FY19 Q1 – Submit journal article to Wind Energy Science on controls-modeling of stable atmospheric simulations and effect of stability on wake steering. (Quarterly Progress Measure (Regular)) | 100% | 12/31/2018
FY19 Q2 – Modify FLORIS to include model of vortices produced in wake steering and impact on wakes. Release the updated code on NREL’s public github software repository. (Quarterly Progress Measure (Regular)) | 100% | 3/31/2019
FY19 Q3 - Release open-source wind farm control system and analysis tool set to NREL’s public github software repository. (Annual Milestone (Regular)) | 100% | 6/30/2019
FY19 Q4 - Release of open-source offshore floating controller to public software repository including a report documenting the design and use of the controller. (Quarterly Progress Measure (Regular)) | 100% | 9/30/2019
Evaluation of open-source offshore floating controller and control model to determine acceptability of approach. (Go/No-Go) |  | 

## Slide 55: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY19 Q4 Project Milestone Status
Work accomplished this quarter: Completed generic turbine controller for use in studies of offshore and floating turbines, this work will be incorporated into collaborative work with system engineering next year. Tool includes methods for automatic tuning of generic controller which includes substantial improvements over existing baselines such as peak shaving and full torque PI control with region switching handled by setpoint fading Initial results of analysis of second phase of Peetz study demonstrate conclusive success in increasing energy gain through wake steering, as well as demonstrating FLORIS’ ability to predict those gains when dynamic considerations are included Public Outreach/Industry Engagement: Organized and held IEA Wind topical expert’s meeting on wind farm control in Amsterdam. Collected expert’s elicitation on wind farm control state of the art and research priorities Jen King, Chris Bay and Andrew Scholbrock will present papers on wind farm control research at the American Controls Conference within a well-attended invited session co-organized by NREL Eric smiley submitted for review Simley, E., Fleming, P., and King, J.: Design and Analysis of a Wake Steering Controller with Wind Direction Variability, Wind Energ. Sci. Discuss., https://doi.org/10.5194/wes-2019-35, in review, 2019. FLORIS use continues to expand across research community and industry
90-Day Outlook: Study will be completed of new generic controller applied to a variety of offshore floating systems Collaboratively with wake steering, investigate the inclusion of important additional physical effects into FLORIS including deep-array effects and near-wake specific models. Comparison with offshore SCADA data will be used to assess various possible corrections Upcoming Public Outreach/Industry Engagement: Expect to submit two journal papers in near future, one on further physics improvements in FLORIS and an additional journal paper (together with wake dynamics) detailing results of wake steering campaign at Peetz and comparison with new FLORIS models Will begin preparing a report/journal or conference paper on results of IEA Wind topical expert’s meeting and expert elicitation

## Slide 56: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 57: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY19 Q4 Project Overview
Project Attributes
Budget
Total: $250,000 (Carryover: $0, 2019 Budget Authority: $250,000)
Project PI
Jennifer King Jennifer.King@nrel.gov 303-384-7086
DOE Lead
Mike Derby Michael.Derby@ee.doe.gov
Key Personnel
Paul Fleming Jennifer King Alan Wright Eric Simley Christopher Bay
Project Summary
Wind turbines in a wind farm typically operate individually to maximize their own performance without explicitly taking into account information from nearby turbines. To enable cooperation to achieve farm-level objectives, turbines will need to use information from nearby turbines to optimize performance, ensure resiliency when sensors fail, and adapt to changing local conditions.
Project Objective & Impact
The objective of this project is to deploy a Collective Consensus Controller for Performance Optimization (C3PO), on a utility-scale wind farm in the field to demonstrate the potential power performance gain in a wind farm. This project will be done in coordination with an industry partner, Renewable Energy Systems (RES). C3PO is a cooperative wind farm controller that incorporates information from local sensors in real-time to better align turbines to the prevailing wind direction to improve performance of individual turbines.

## Slide 58: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | No costing planned in FY19.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | No milestones in FY19.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 59: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $250,000; FY19 Beginning Uncosteds: $0)
Subcontracts/Commitments:
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 0 | 0 | 0 | 0 | 250000
Total Funding Level (Cum.) | 0 | 0 | 0 | 0 | 250000
FY19 Funding Received (Cum.) | 0 | #N/A | #N/A | #N/A | 250000
Projected Recipient Spend Plan (Cum.) | 0 | 0 | 0 | 0 | 0
Actual Accrued or Invoiced Costs (Cum.) | 0 | 0 | 0 | 0 | 0
Actuals + Commitments (Cum) | 0 | 0 | 0 | 0 | 0
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 60: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
No Milestones in FY19 |  | 

## Slide 61: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY19 Q4 Project Milestone Status
Work accomplished this quarter: Public Outreach/Industry Engagement:
90-Day Outlook: NREL will complete baseline collection of data from multiple sites by 12/31/2019. This data will be uploaded to internal databases that will allow for easy analysis with respect to the collective consensus control software as well as comparison between the wind farms. Upcoming Public Outreach/Industry Engagement: NREL will begin writing a report for RES on the performance of collective consensus control at their different wind farms.

## Slide 62: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 63: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization FY19 Q4 Project Overview
Project Attributes
Budget
Total: $1,135,162 (Carryover: $355,162, 2019 Budget Authority: $780,000)
Project PI
Garrett Barter garrett.barter@nrel.gov 303-384-7102
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Garrett Barter Jennifer King Ryan King Pietro Bortolotti Peter Graf Evan Gaertner
Project Summary
The SEO initiative develops an analysis platform and research capability to capture important system interactions to achieve a better understanding of how to improve system-level performance and achieve system-level cost reductions. The effort incorporates advances in computational algorithms, simulation methods, physics-based improvements, cost and performance modules to assess new technology opportunities and advance the state-of-the-art and best practices in multi-disciplinary design, analysis and optimization (MDAO) for wind energy applications.
Project Objective & Impact
The objectives of SEO include: Advance the state-of-the-art in MDAO for wind energy applications in terms of enabling wind turbine and plant design that 1) incorporates increased system scope to investigate trade-offs in a variety of aspects of system design and operation, 2) incorporates models of increased fidelity to allow more realistic and accurate representation of the system in the upfront optimization process, and 3) incorporates more sophisticated workflows (i.e., multi-level, multi-fidelity optimization under uncertainty) for more efficient and robust system design. Demonstrate the value of MDAO for improving overall wind turbine and plant performance and cost through a series of case studies. Promote adoption of MDAO and related techniques by industry through demonstration of value and publication of best practices.

## Slide 64: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 65: NREL Wind - 1.3.6.401 - Systems Engineering & Optimization FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $780,000; FY19 Beginning Uncosteds: $355,162)
Subcontracts/Commitments:
BYU subcontract with Prof. Andrew Ning
CU subcontract with Prof. Peter Hamlington
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 355162 | 312121 | 339623 | 311047 | 240501
Total Funding Level (Cum.) | 1135162 | 1135162 | 1135162 | 1135162 | 1135162
FY19 Funding Received (Cum.) | 355162 | 510565 | 745162 | 940162 | 1135162
Projected Recipient Spend Plan (Cum.) | 0 | 162907 | 411497 | 621735 | 899818
Actual Accrued or Invoiced Costs (Cum.) | 0 | 167603 | 329549 | 606148 | 866483
Actuals + Commitments (Cum) | 0 | 198444 | 405539 | 629115 | 894661
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 66: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
WETO.1.3.6.401, FY19 Q1: Complete and submit conference papers for AIAA SciTech 2019 on the IEA Wind Task 37 wind plant layout optimization case study and the application of statistical methods to turbulent inflow modeling for wind turbine loads analysis. (Quarterly Progress Measure (Regular)) | 100% | 12/31/2018
WETO.1.3.6.401, FY19 Q3 Q2: Demonstrate ability to simulate effects of mild terrain with attached flows on intra-plant flow fields and examine impact on array losses and overall plant energy production. (Quarterly Progress Measure (Regular)) | 100% | 3/31/2019
WETO.1.3.6.401, FY19 Q2 Q3: Complete study on aero-structural optimization of a wind turbine rotor that incorporates extreme loads estimation from aeroelastic simulations using advanced statistical techniques such as importance sampling. (Quarterly Progress Measure (Regular)) | 100% | 6/27/2019
WETO.1.3.6.401, FY19 Q4: Complete study incorporating the impacts of wake steering on turbine loads into an optimization study of wind plant yaw control optimization. (Annual Milestone (Regular)) | 100% | 9/30/2019

## Slide 67: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization FY19 Q4 Project Milestone Status
Work accomplished this quarter: Completed study to include additional blade loads from partial waking as a constraint in wind plant layout optimization, led by BYU for Q4 milestone Completed NAWEA WindTech papers: 1) Layout optimization in complex terrain, 2) Loads-aware layout optimization (same as Q4 milestone), and 3) Third paper on usage of a common ontology for blade systems engineering was withdrawn and will be submitted later for TORQUE Significantly simplified WISDEM install process to “conda install wisdem” which will make collaboration with external industry and collaborators easier Finalized plans and presentations for Oct 2019 Systems Engineering Workshop hosted by CENER in Pamplona, Spain Public Outreach/Industry Engagement:
90-Day Outlook: Attend the IEA Wind Task 37 Meeting and the 2019 Systems Engineering Workshop hosted by CENER in Pamplona, Spain. Present work related to the 15MW Reference Turbine, a common ontology for blade systems engineering, and a tutorial for WISDEM Present two papers at NAWEA WindTech: 1) Layout optimization in complex terrain, 2) Loads-aware layout optimization Complete AIAA papers related to 1) usage of Importance Sampling to estimate extreme loads within a design loop 2) Multiple collaborative papers with Sandia on UQ methods applied to wind energy Collaborate on the design of the 15MW Reference Wind Turbine Submit multiple abstracts to the TORQUE conference Upcoming Public Outreach/Industry Engagement: Engage the awardees of the Lightweight Drivetrain FOA 1981 about using WISDEM to model the LCOE impacts of their designs

## Slide 68: NREL Wind – 1.3.6.402 - Multi Physics Model Validation & UQ Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 69: NREL Wind – 1.3.6.402 - Multi Physics Model Validation & UQ FY19 Q4 Project Overview
Project Attributes
Budget
Total: $607,938 (Carryover: $177,938, 2019 Budget Authority: $430,000)
Project PI
Jason M. Jonkman Jason.Jonkman@nrel.gov 303-384-7026
DOE Lead
Mike Derby Michael.Derby@ee.doe.gov 202-586-6830
Key Personnel
Paula Doubrawa Paula.Doubrawa@nrel.gov Amy Robertson Amy.Robertson@nrel.gov Kelsey Shaler Kelsey.Shaler@nrel.gov
Project Summary
Enable the development of advanced wind-plant technology by leveraging knowledge, data, and HFM results from the broader A2e initiative to verify, validate, and improve physics-based engineering tools at both the turbine and plant levels.
Project Objective & Impact
Systematically V&V physics-based engineering tools by comparisons to HFM and experimental data to quantitively understand their applicability, accuracy, and uncertainties Improve the physics of engineering tools to expand the tools’ applicability where limitations hinder technology advancement Engage in international V&V collaboratives among research laboratories, academia, and industry to further advance engineering models.

## Slide 70: NREL Wind – 1.3.6.402 - Multi Physics Model Validation & UQ FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 18% underspent. Actual spending has been less than planned in Q3 and Q4 because (1) core staff were not available as planned and (2) the initiation of the DNV-GL JIP on “turbulence modeling” has been delayed. Regarding (1), less time-critical work (not impacting milestones) has been postponed to, and resulted in more carryover into, FY 2020.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: (1) Lab – Project or Budget Planning; (2) Lab - External Project Partner
Mil. | Q1 | Q4 milestone is delayed one quarter. The Q4 milestone is slightly delayed, commensurate with the underspending. All of the HFM and FAST.Farm simulations have been completed, the results have been processed and the journal manuscript has been initiated. The journal manuscript will be completed soon and submitted by the end of October rather than September.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab – Project or Budget Planning

## Slide 71: NREL Wind - 1.3.6.402 - Multi Physics Model Validation & UQ FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $430,000; FY19 Beginning Uncosteds: $177,938)
Subcontracts/Commitments:
N/A
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 177938 | 136163 | 173244 | 185913 | 213174
Total Funding Level (Cum.) | 607938 | 607938 | 607938 | 607938 | 607938
FY19 Funding Received (Cum.) | 177938 | 263608 | 392936 | 500438 | 607938
Projected Recipient Spend Plan (Cum.) | 0 | 114358 | 223074 | 356301 | 483137
Actual Accrued or Invoiced Costs (Cum.) | 0 | 127445 | 219692 | 314525 | 394764
Actuals + Commitments (Cum) | 0 | 127445 | 219692 | 314525 | 394764
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 72: NREL Wind – 1.3.6.402 - Multi Physics Model Validation & UQ FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
WETO.1.3.6.402, Q1: Complete the sensitivity assessment of wind-turbine engineering-model predictions to identify the aerodynamic inputs with high variability/uncertainty that are most influential on loads and power and document the findings in an AIAA SciTech 2019 paper by December 31, 2018. (Quarterly Progress Measure (Regular)) | 100% | 12/14/18
WETO.1.3.6.402, Q2: Within the IEA Wind Task 29 Aerodynamics international V&V collaborative, complete the first round of comparisons between OpenFAST’s predictions of wind turbine loads and power against other engineering-model solutions, HFM computations, and experimental data from the DanAero database and share the results at the Task 29 annual meeting by March 31, 2019. (Quarterly Progress Measure (Regular)) | 100% | 3/14/19
WETO.1.3.6.402, Q3: Within the IEA Wind Task 31 WakeBench international V&V collaborative, complete the validation of FAST.Farm’s predictions of wind turbine power, turbine loads, and wake deficits and meandering against other engineering-model solutions, HFM computations, and experimental data from SWiFT and share the results at the Task 31 annual meeting by June 30, 2019. (Quarterly Progress Measure (Regular)) | 100% | 5/21/19
WETO.1.3.6.402, Q4: Complete the validation FAST.Farm’s predictions of wind turbine power and loads against HFM solutions and experimental data from the OWEZ offshore wind plant to quantify its applicability, accuracy, and uncertainty and document the development of FAST.Farm and validation results in a journal manuscript submitted by September 30, 2019. Journal publication of the final accepted manuscript is expected in FY 2020. (Annual Milestone (Regular)) | 90% | Expected by 10/31/19

## Slide 73: NREL Wind – 1.3.6.402 - Multi Physics Model Validation & UQ FY19 Q4 Project Milestone Status
Work accomplished this quarter: Submitted a merit-review application for a 4-year project starting in FY 2020 titled, “Integrated Systems Design and Analysis – Modeling and Validation for Offshore Wind (ISDA-OSW),” which merges extensions to this ISDA-MV project and the ISDA-OSW project (NREL PI: Amy Robertson) that are both ending in FY 2019 Developed the FY 2020 AOP for the new combined ISDA-OSW task. Within the IEA Wind Task 29 Phase IV (Aerodynamics) project focused on the three-way V&V of rotor aeroelastics through intercomparison of HFM, engineering models, and data from the DanAero field experiment, improved the OpenFAST model to better match the turbine description and ran and submitted updated load-case simulation results for the first and second round of comparisons. Within the IEA Wind Task 31 Phase III (WakeBench) project focused on the three-way V&V of wind-plant aerodynamics through intercomparison of HFM, engineering models, and data from the A2e SWiFT field experiment, improved the OpenFAST / FAST.Farm model of the V27 turbine and SWiFT wind farm based on improved calibration of the model to measurement data, reran and submitted load-case simulations, and discussed the results at Task 31 net meetings. In partial fulfillment of the F2019 Q4 milestone, validated the wind turbine blade, drivetrain, and tower structural loads predicted by FAST.Farm by comparisons to coupled SOWFA-OpenFAST simulations. Made two algorithmic changes to FAST.Farm to improve its robustness, including allowing wake planes to pass each other and leave the domain without triggering errors. Initiated HFM actuator-disk simulations to study the wake response under high thrust conditions, the results of which will be used to improve the near-wake correction model in, and robustness of, FAST.Farm. Initiated the sensitivity assessment of engineering model predictions of loads and power for turbines in a small wind farm to variations in wind inflow and wake parameters to identify the most influential parameters. Public Outreach/Industry Engagement: Submitted for publishing the final Wind Energy Science journal paper on the sensitivity assessment of uncertain turbine wind-inflow and aero-servo-elastic properties on power and structural loads. In partial fulfillment of the FY 2019 Q4 milestone, initiated a Wind Energy journal paper on the development and validation of FAST.Farm. Coordinated with USTUTT SWE regarding validation of FAST.Farm using data from a met tower and two Senvion 5-MW turbines atop fixed-bottom jackets at the alpha ventus offshore wind farm. Continued working with Envision Energy and Makani under WFOs to further support the development, V&V, and application of OpenFAST. Continued working with Vestas, IFE/NextFarm, and Equinor under WFOs to further support the development, V&V, and application of FAST.Farm. Also, planned a SOW for a new WFO with Shell regarding related wind farm modeling and V&V using FAST.Farm.

## Slide 74: NREL Wind – 1.3.6.402 - Multi Physics Model Validation & UQ FY19 Q4 Project Milestone Status
90-Day Outlook: In fulfillment of the FY 2020 Q1 milestone, run and submit updated and additional load-case simulations using OpenFAST in support of the three-way V&V collaborative involving DanAero data within IEA Wind Task 29 (Aerodynamics) and discuss the results at Task 29 net meetings. In partial fulfillment of the FY 2020 Q3 milestone, develop OpenFAST and FAST.Farm models of three wind turbines at the Peetz Table wind farm and identify experimental datasets that will be used for validation. Attend the IEA Wind Task 31 (WakeBench) meeting held in conjunction with the NAWEA / WindTech 2019 conference. Develop an improved near-wake correction model in FAST.Farm based on HFM actuator-disk simulations under high thrust conditions. Finalize the super controller implementation in FAST.Farm and complete the FAST.Farm user documentation. Finalize the approach and begin running TurbSim and FAST.Farm simulations for the sensitivity assessment of engineering model predictions of loads and power for turbines in a small wind farm to variations in wind inflow and wake parameters to identify the most influential parameters. Upcoming Public Outreach/Industry Engagement: In fulfillment of the FY 2019 Q4 milestone, submit a draft Wind Energy journal paper on the development and validation of FAST.Farm. Co-author a draft journal paper on the three-way V&V collaborative involving A2e SWiFT data within IEA Wind Task 31 (WakeBench). In partial fulfillment of the FY 2020 Q3 milestone, submit an extended abstract for a paper to be presented at TORQUE 2020 on the validation of FAST.Farm against data from the Peetz Table wind farm. Submit an extended abstract for a paper to be presented at TORQUE 2020 on wake response under high thrust conditions, including an improved near-wake correction model in FAST.Farm. Publicly release FAST.Farm to the wind community for the first time. Continue coordinating with USTUTT SWE regarding validation of FAST.Farm using data from a met tower and two Senvion 5-MW turbines atop fixed-bottom jackets at the alpha ventus offshore wind farm. Continue working with Envision Energy and Makani under WFOs to further support the development, V&V, and application of OpenFAST. Continue working with Vestas, IFE/NextFarm, Equinor, and Shell under WFOs to further support the development, V&V, and application of FAST.Farm. Initiate the follow-on extension to the DNV-GL JIP on “validation of turbulence models”.

## Slide 75: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes
2/6/2019 | A.Robertson |  | N/A | Q3 Milestone Change – Reflected on Slide 49

## Slide 76: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY19 Q4 Project Overview
Project Attributes
Budget
Total: $1,423,561 (Carryover: $753,561, 2019 Budget Authority: $670,000)
Project PI
Amy Robertson Amy.Robertson@nrel.gov 303-384-7157
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Fabian Wendt Jason Jonkman Nathan Tom Manuela Bohm
Project Summary
To advance innovative offshore wind technologies to commercial maturity, the current suite of modeling tools used for designing offshore wind systems needs to be validated with high-quality datasets under a variety of conditions. Validation will assess the accuracy of the modeling tools, provide a better understanding of their uncertainties, identify needed areas of improvement, and increase their acceptance within industry and wind research communities. The level of trust and acceptance of the tools directly translates to the perceived risk in the project, which impacts design methodology and bankability, both significant cost drivers. Validated modeling tools can then be used to develop optimized designs to reduce costs and achieve the Wind Vision scenarios. To address the need for validated offshore wind modeling tools, the Offshore Code Comparison, Collaboration, Continued, with Correlation (OC5) was initiated. OC5 is an international research project run under the International Energy Agency (IEA) Wind Task 30, and this DOE task supports NREL’s leadership and participation in the project, as well as a new extension that will run from January 2019 to January 2023 (OC6 – including unCertainty). The project involves participants from across the offshore wind industry field, including offshore wind designers, consultants, certifiers, developers, and research institutions.
Project Objective & Impact
The objectives of the project are to: Validate engineering-level offshore wind modeling tools through the comparison of simulation results to higher-fidelity models and measurement data from a variety of experimental campaigns of varying structure types and conditions. Develop datasets needed to address specific validation objectives identified as critical to the accurate use of offshore wind modeling tools. Improve the physics of the offshore wind modeling tools to address both the outcomes of validation campaigns and the technology innovations that require the expansion of the tools’ applicability and capabilities (where limitations hinder technology advancement). Identify research and development needs beyond the scope of this project to better understand the physics of offshore wind systems and how to appropriately integrate these attributes into the modeling tools.

## Slide 77: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | The fourth quarter milestone of releasing a new public offshore wind validation dataset of component-level hydrodynamic loads on floating offshore wind systems is delayed due to delays at the wave tank that is performing the validation campaign. The work is progressing, and the campaign is expected to be concluded in the next month.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab - External Project Partner

## Slide 78: NREL Wind - 1.3.6.403 - Modeling and Validation for Offshore Wind FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $670,000; FY19 Beginning Uncosteds: $753,561)
Subcontracts/Commitments:
A purchase order worth $301K has been signed with Texas A&M Engineering Experiment Station for the work effort titled “Component-Level Hydrodynamic Validation Campaign for Floating Wind”. The term of the PO is from October 2019.
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 753561 | 716813 | 737684 | 334158 | 407921
Total Funding Level (Cum.) | 1363561 | 1363561 | 1363561 | 1363561 | 1423561
FY19 Funding Received (Cum.) | 753561 | 875093 | 1058559 | 1211061 | 1423561
Projected Recipient Spend Plan (Cum.) | 0 | 179149 | 567577 | 985562 | 1144108
Actual Accrued or Invoiced Costs (Cum.) | 0 | 158280 | 320875 | 676030 | 993580
Actuals + Commitments (Cum) | 0 | 158280 | 320875 | 876903 | 1015640
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 79: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
1.3.6.403, Q1: Complete the validation study utilizing structural loads data from the full-scale Alpha Ventus Jacket by comparing simulated responses, provided by a variety of participants in the OC5 project, against field measurements for near and above-rated wind conditions (where tuned controller matches commercial system) and two operations (yawing, shut-down) – completing Phase III of OC5. Submit an abstract to an offshore wind conference (ISOPE or OMAE) to present the findings of the validation study in the summer of 2019. (Quarterly Progress Measure (Regular)) | 100% | 12/24/2018
1.3.6.403, Q2: With the help of OC6 project participants, define the overall validation objectives and procedures for Phase I of the OC6 project, which is focused on the nonlinear hydrodynamic loading in a floating semisubmersible offshore wind support structure. Release a description document for Phase I to project participants by March 31, 2019, providing the overall objectives of the phase, a description of the tests and data available for the validation, and the validation process that will be implemented. (Quarterly Progress Measure (Regular)) | 100% | 2/10/2019
1.3.6.403, Q3: Define a set of load cases that can be used to validate the nonlinear dynamic behavior of a floating semisubmersible, through a three-way validation between FAST simulations, higher-fidelity computational fluid dynamics (CFD) simulations, and test measurements. Previous validation work has shown the need for more dedicated load cases that match the capabilities of CFD tools. These load cases would then be implemented in the component-level test campaign to be performed in FY19. An abstract will be developed by June 30, 2019 summarizing the findings for presentation at the IOWTC conference in November 2019. (Quarterly Progress Measure (Regular)) | 100% | 6/30/2019
1.3.6.403, Q4: Release a new public offshore wind validation dataset that can be used by researchers interested in the modeling of component-level hydrodynamic loads on floating offshore wind systems by performing a new test campaign at a wave tank in the United States. The test campaign will be used to develop and highlight national capabilities for offshore wind testing through a set of fixed and forced motion tests of support structure components of different sizes and configurations, with a focus on distributed hydrodynamic load measurements. Upload the data to the DOE Data Archive and Portal, with associated documentation, by Sept. 30, 2019 for public use. (Annual Milestone (Regular)) | 80% | 

## Slide 80: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY19 Q4 Project Milestone Status
Work accomplished this quarter: OC6: Work on Phase I of OC6 continued, which is focused on better understanding nonlinear hydrodynamic load underprediction in offshore wind design tools for semisubmersible designs. Load cases 1-4 have now been simulated by the group. The CFD group for OC6 has continued to work on a regular wave load case for Phase I. The goal is to use the information from the CFD group to help inform the load under-prediction by the engineering models. However, first achieving good, consistent results from the CFD tools is a difficult process. A more prescriptive modeling approach has been initiated to help improve agreement between the participants. A new post-doc was hired at NREL to focus on the CFD analysis work for this project (Lu Wang). A DAP site was created for the OC5 project. New Validation Campaign: The component-level validation campaign was initiated at the Offshore Technology Research Center at Texas A&M University. The models have been built and installed, calibration checks have been performed, and the system set-up improved to address testing needs. Tests have been started, and the full test matrix is expected to be completed by the end of October. A new contract was signed with Texas A&M to broaden the test cases and provide better checks to ensure the understanding of the results. A paper summarizing the development of the bichromatic wave cases for the validation campaign was completed and accepted by the International Offshore Wind Technology Conference (IOWTC). A DAP site was created for the OC6 project, which will also house the data from this validation campaign. Public Outreach/Industry Engagement: An Open Test Day was held at the OTRC on September 24th, allowing the public to witness the new floating wind, component-level validation campaign and understand how it fits into the goals of the OC6 project. Ten people from the offshore industry attended, representing the following companies: Shell, DNV GL, SBM Offshore, Bentley, MARIN, Atkins, and London Offshore Consultants. The work of OC6 was presented at the IEA Wind Executive Committee meeting in Copenhagen, Denmark on September 17 – 19. Matt Hall attended the kick-off meeting of the COREWIND project as an NREL advisor on September 2-3, 2019. COREWIND is an EU project focused on reducing the cost, and increasing the performance, of floating wind technology, with specific emphasis on moorings and O&M.

## Slide 81: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY19 Q4 Project Milestone Status
90-Day Outlook: OC6: The OC6 group will initiate simulations across all five of the load case groups for Phase I. The work of Phase I is expected to be completed in Q2 of FY20. After the regular wave case is completed, the CFD group will move on to a bichromatic wave case, which will focus directly on the nonlinear modeling issue. An abstract will be submitted for presentation of the OC6 Phase I work at the TORQUE conference (which will be held in May, 2020). NREL will begin development of the specification for Phase II of OC6, which is focused on higher-fidelity modeling of soil-structure interaction for fixed-bottom offshore wind systems. NREL will initiate development of DAP sites for the OC3 and OC4 projects. The next in-person meeting of the OC6 project will be held in conjunction with the IOWTC conference on Nov. 7th in Malta. New Validation Campaign: Complete the validation campaign at the OTRC facility, and get the data uploaded to the DAP. Upcoming Public Outreach/Industry Engagement: Senu Sirnivas will attend the bi-annual joint meeting of the CFD JIP for offshore systems. Amy Robertson will present the paper on the new bichromatic wave cases for the floating wind hydrodynamic validation campaign at the IOWTC conference, which will be held from Nov. 4-6 in Malta. Amy Robertson will attend the IECRE/TC88 Joint Working Forum on Model Validation on Oct. 14-15, 2019 in Denmark. The purpose of the meeting is to discuss steps to standardize and develop conformity assessment of model validation in the wind industry. The travel is funded by a different project, but the experience and feedback is relevant to the OC6 project, which is focused on offshore wind validation.

## Slide 82: NREL Wind – 1.3.9.401 - A2e EMC Support Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 83: NREL Wind – 1.3.9.401 - A2e EMC Support FY19 Q4 Project Overview
Project Attributes
Budget
Total: $34,811 (Carryover: $34,811, 2019 Budget Authority: $0)
Project PI
Paul Veers paul.veers@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov
Key Personnel
Paul Veers Daniel Laird
Project Summary
A2E is a major initiative utilizing an innovative DOE and national laboratory collaborative to develop a comprehensive, multiyear, R&D program to: 1) achieve wind plant system cost and performance improvements that attain LCOE parity with fossil fuel generation, and 2) develop the analysis methods and tools necessary to assess the macro and micro impacts of high wind penetration scenarios on a national scale in support of future high penetration deployment scenarios. It addresses the areas of atmospheric science, wind plant interactions and technology development. Each of the three major labs involved in A2e (NREL, PNNL, SNL) has one or more member from the lab on the A2e Executive Management Committee (EMC).
Project Objective & Impact
The objective of this project is to provide laboratory-based leadership to the management of the A2e initiative through travel and participation in the EMC meetings.

## Slide 84: NREL Wind – 1.3.9.401 - A2e EMC Support FY19 Q4 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 30% overspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab - Project or Budget Planning
Mil. | Q1 | No milestones required.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 85: NREL Wind - 1.3.9.401 - A2e EMC Support FY19 Q4 Project Financial Status
Project Financials (FY19 Budget Authority: $0; FY19 Beginning Uncosteds: $34,811)
Subcontracts/Commitments: Subcontract with Canvas Consulting (John Meissner)
Chart: 
| 0 | FY19 Q1 | FY19 Q2 | FY19 Q3 | FY19 Q4
Uncosted & Uncommitted Funds | 34811 | 8660 | 4726 | 1152 | 1747
Total Funding Level (Cum.) | 34811 | 34811 | 34811 | 34811 | 34811
FY19 Funding Received (Cum.) | 34811 | 34811 | 34811 | 34811 | 34811
Projected Recipient Spend Plan (Cum.) | 0 | 8557 | 15903 | 19576 | 24412
Actual Accrued or Invoiced Costs (Cum.) | 0 | 16646 | 22294 | 32253 | 31658
Actuals + Commitments (Cum) | 0 | 26151 | 30085 | 33659 | 33064
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 86: NREL Wind – 1.3.9.401 - A2e EMC Support FY19 Q4 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
No Milestone Required |  | 

## Slide 87: NREL Wind – 1.3.9.401 - A2e EMC Support FY19 Q4 Project Milestone Status
Work accomplished this quarter:
90-Day Outlook: Support DOE on FY20 A2e AOP planning