## Slide 1: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 2: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Overview
Project Attributes
Budget
Total: $388,517 (Carryover: $388,517, 2020 Budget Authority: $0)
Project PI
Nicholas Hamilton nicholas.Hamilton@nrel.gov 303-384-6945
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Nicholas Hamilton
Project Summary
The extent to which modern wind plant control strategies induce additional aeroacoustic emissions from additional separation and other flow interaction dynamic effects is not known, and may have a significant impact on future wind plant development and wind turbine siting. Off-nominal rotor control by prescribed yaw misalignment is expected to induce periodic flow separation locally along the rotor blades and change the aerodynamic interaction with the local flow field. Given public concerns about wind turbine noise and the need for observational data required for regulators to establish noise restrictions, potential acoustic emissions resulting from active control must be understood prior to commercial deployment and the development of practical noise reduction methods and technology. Additional downstream acoustic propagation effects introduced by active yaw and or thrust control must be investigated and understood for modern wind plant control strategies to be successfully implemented at the utility scale.
Project Objective & Impact
Aeroacoustics project objectives are focused on quantifying the additional acoustic emissions introduced by implementing modern wind turbine and wind plant control strategies. Acoustic noise produced by wind turbines is one of the limiting factors on their operation and one of the constraints placed on development of wind plants. Specific FY19 and FY20 objectives are to: Experimentally quantify the aeroacoustic emissions of a utility scale wind turbine operating under yawed conditions. Determine the nature of the changes to the overall sound pressure level directivity under the influence of yaw misalignment. Update and validate aeroacoustic modeling software to integrate into current OpenFAST framework against observational data collected experimentally. Disseminate findings of aeroacoustic field observations for a utility-scale wind turbine operating under prescribed yaw offsets though peer-reviewed journal publications

## Slide 3: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 71% underspent. Project is underspent due to a delay in the acquisition of instrumentation and equipment required to execute the experimental test plan. The scope of measurements planned for the Aeroacoustics project requires that extra care be placed on instrument selection, to ensure compliance with relevant measurement standards and to ensure data quality throughout the project. Instrumentation acquisition is currently under way. Purchase orders for acoustic instrumentation and data acquisition systems have been placed. Delivery of equipment to NREL is expected by February 5, 2020.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab – Procurement/Acquisition Delay
Mil. | Q1 | Schedule is on track – quarterly milestone/deliverable met on time. Despite the delay in purchasing equipment, the Q1 milestone goal was to identify the proper instrumentation to purchase. That was accomplished.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 4: NREL Wind - 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $0; FY20 Beginning Uncosteds: $388,517)
Subcontracts/Commitments: The procurement process has been initiated for acoustic instrumentation and data acquisition platforms to make measurements in support of the Aeroacoustics project. Project budget for equipment was scheduled for FY19Q4 and FY20Q1 but has been delayed to ensure that the correct instrumentation is acquired. Purchase orders for acoustic recording equipment (Brüel & Kjær microphones, preamplifiers, signal conditioners, ~$39k), data acquisition systems (National Instruments ~$32k), processing software (Delta ~$2k), cabling/soundboards/hardware (~$14k), are being processed. All equipment is scheduled to arrive in January/February and will not interfere with project milestones.
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 388517 | 293248 | 0 | 0 | 0
Total Funding Level (Cum.) | 388517 | 388517 | 388517 | 388517 | 388517
FY20 Funding Received (Cum.) | 388517 | 388517 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 170532 | 249832 | 319459 | 388517
Actual Accrued or Invoiced Costs (Cum.) | 0 | 49379 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 95269 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 5: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: Specify instrumentation needs to make point measurements for time- and frequency-domain assessment of aeroacoustic emissions of GE 1.5 MW wind turbine | 100% | 12/23/19
Q2: Deploy instrumentation around DOE-owned GE 1.5 MW wind turbine at NREL Flatirons campus and begin data acquisition, quality assurance, and quality control processes for audio data. | 15% | 
Q3: Complete technical report on aeroacoustic code verifications using the updated framework of aeroacoustics module and physics models to interface with NREL modeling tools. |  | 
Q4: Submit article to peer-reviewed scientific publication detailing the aeroacoustic tests performed as part of the project and quantifying the changes in acoustic emission introduced by operating a utility-scale wind turbine in yawed conditions. |  | 

## Slide 6: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Milestone Status
Work accomplished this quarter: A review of all measurement standards for wind turbine noise testing (IEC 61400-11, IOA NWG, 2013), sound level meters (IEC 61672), low-frequency noise (ANSI/ASA S12.9-2016/Part 7), and characterization of acoustic effects (NT ACOU 112, 2002) was undertaken to ensure that all instrumentation acquired complies with the standards and that measurement data will be of sufficient quality to benefit the wind turbine noise research community. Measurement locations, data acquisition system configuration, and cabling for power and communications were specified in sufficient detail to recommend specific equipment choices. Testing locations were visually inspected for access, site suitability, and accuracy. All test locations were reviewed with US Fish and Wildlife (measurements will take place on Rocky Flats National Wildlife Refuge). The test plan and measurement locations have been communicated with US Fish and Wildlife and are included in the renewed Special Use Permit for NREL. A project review under NEPA has been initiated with DOE/NREL and is expected to be complete by Feb. 7, well before deployment of instrumentation. Public Outreach/Industry Engagement: Wind turbine noise consultants, Delta and FORCE, have been contacted to discuss project summary and data processing/analysis standards for acoustic metrics beyond standard noise test (low-frequency noise, amplitude modulation, impulsivity, and tonality)
90-Day Outlook: FY20 Q2 will be focused on testing functionality, connectivity, and compliance of all instrumentation and equipment required to execute the test plan developed in FY19 Q4. In the first part of the quarter, a detailed schedule for observations will be produced to guide the testing of instrumentation on site before deployment for measurements. Any modifications to the test plan as required by outside constraints (sensor placement, site access, coordination with other research) will be factored into and incorporated into the working test plan document. Upcoming Public Outreach/Industry Engagement: Continued engagement with the wind turbine aeroacoustics research community will inform instrument specification and acquisition and avoid pitfalls in data collection and processing. No public dissemination of test results is planned for the aeroacoustics project until FY20 Q3.