## Slide 1: Quarterly Report Due Dates
FY19 Q1 reports Due to HQ by COB: 1/14/19
FY19 Q2 reports Due to HQ by COB: 4/12/2019
FY19 Q3 reports Due to HQ by COB: 7/15/2019
FY19 Q4 reports Due to HQ by COB: 10/16/2019
PLEASE follow the file-name saving format on slide 2

## Slide 2: Quarterly Reporting Template Preparation Overview (delete slide when submitting final)
The Technical Quarterly Progress Reports should be prepared keeping in mind that serve an important purpose:
To provide the technical management team a concise record of the progress made during the reporting period and any problems encountered that would affect the accomplishment of goals established for the work, impact the project schedule, or may require redirection. These reports are intended to be stand-alone documents, with sufficient technical detail that one unfamiliar with the project can quickly understand the scope, context, and status of the work.
Reporting
This template contains a Project Status Overview slide, a Project Modification Tracking slide (where necessary), and 3 slides for each project status update. Slides for all projects under a given WBS Activity level (e.g. - 01.02.03.04.567 = 01(Office).02(Program).03(Activity).04(Sub-activity).567(Project)) should be saved together. For example, all projects that begin with 01.02.03.xx.xxx would be submitted together as one PowerPoint deck)
File Name: (the first digit in the WBS is a Wind/Water identifier, you do NOT need to include this)
Lab_Program_WBS_FY_Quarter.ppxt
Using the WBS Example Above: NREL_Wind_2.3_FY19_Q1.pptx
DUE DATE: Reports are due 10 business days after the end of each FY quarter. (see dates on previous slide)
Roles and Responsibilities:
Each sub-deck should be completed by the PI conducting the work
Lab leads should compile, QC, assign issue categories to R/Y stoplights.
All slide decks should be submitted to HQ via email to raphael.tisch@ee.doe.gov no later than the dates listed in the NOTES below.

## Slide 3: Quarterly Reporting Template Preparation Overview (delete slide when submitting final)
Stop Light color codes:
For the relevant sections, stoplight assessments should be determined by the PI (with assistance from the financial team, if necessary).
Financial Status
    Green = Cumulative spend plan variance is between 15.5% and -15.5%
    Yellow = Cumulative spend plan variance between +15.5% and +35.5% (overspend)
    Yellow = Cumulative spend plan variance is between -15.5% and -35.5%
    Red = Cumulative spend plan variance is <-35.5% or >+35.5% (overspend)
Schedule/Milestones
    Green = Milestone(s) is/are met on time, as noted in the AOP, or other official documentation.
    Yellow = Milestone(s) deadline delayed by 1 quarter
    Red = Milestone(s) is/will be delayed by two or more quarters
Project Reviews:
Each quarter a lab submits quarterly reports, HQ Technical Leads and Monitors are required to review and provide feedback to the labs on quarterly progress for those projects that are behind schedule. In addition, ALL submissions undergo a thorough review by the Quarterly Report Process Lead to ensure quality and sufficiency of details provided.

## Slide 4: Issue Categorization (delete slide when submitting final)
Leads for the Wind and Water Programs at the National Labs are responsible for assigning issue categories to all projects with Red or Yellow Milestones or Financials. Issue Category Assignments should NOT be made by the project PI.
Issue categories should be noted on the STATUS OVERVIEW SLIDE, See Template Slide 6 (overview)
Issue Category | Assignment Rational
HQ - Funding Delay/Rebalance | Milestones or financial targets missed due to funding delays from HQ, or is related to a programmatic budget rebalance.
HQ - Guidance | Milestones or financial targets missed due to HQ directing a change to the project scope or budget
HQ - Action/Decision Pending | Milestones or financial targets missed due to pending HQ Action or Decision
Lab – Administrative | Milestones or financial targets missed due to lab internal accounting processes (i.e. billed invoice to the wrong task #, forgot to apply time to task, etc.)
Lab – Procurement/Acquisition Delay | [Pre-award issue category] Milestones or financial targets missed due to delays developing, issuing, or finalizing a subcontract/capital purchase
Lab - Subcontractor | [Post-award issue category] Milestones or financial targets missed due to missing/delayed invoices, deliverables from subcontracted entity

## Slide 5: Issue Categorization (delete slide when submitting final)
Issue Category | Assignment Rational
Lab - External Project Partner | [Post-award issue category] Milestones or financial targets missed due to project partner (FOA awardee, other lab, etc.) deliverable delays, or awaiting guidance/action from project partner
Lab - Project or Budget Planning | Milestones or financial targets missed due to insufficient planning during the AOP development phase (i.e. weak milestones, poor budget development, etc.)
Lab - Project Execution | Milestones or financial targets missed due to under-performance
Lab - Technical Delay | Milestones or financial targets missed due to technical issues relating to hardware malfunctions, unpredictable technical challenges
Lab - Staffing | Milestones or financial targets missed due to lack of staff, departure of staff, temporarily reassigned staff, etc.
Force Majeure | Milestones or financial targets missed due to weather, flooding, wildfire, acts of nature, mass social unrest, etc.
Leads for the Wind and Water Programs at the National Labs are responsible for assigning issue categories to all projects with Red or Yellow Milestones or Financials. Issue Category Assignments should NOT be made by the project PI.
Issue categories should be noted on the STATUS OVERVIEW SLIDE, See Template Slide 6 (overview)

## Slide 6: [Lab] Wind – [WBS # - WBS Category Title] FY18 Q[X] Project Status Overview
Project | Financial Status | Schedule/ Milestones
Project WBS # – Project Title | HQ – Action/Decision Pending | HQ – Action/Decision Pending
1.1.2 - Project Title |  | 
1.1.3 - Project Title | Lab – Project or Budget Planning | Lab - Staffing
1.1.4 - Project Title | Lab – External Project Partner | 
1.2.1 - Project Title |  | 
The fill color in the boxes under each column heading should correspond to the assessments made for each of the projects included in the sub-decks below.
This is intended to be a quick snapshot of the status of all included projects
Issue Categories should be noted on this slide for each RED and YELLOW stoplight
Notes: There should only be ONE WBS overview slide per WBS Deck, summarizing the WBS Status stoplights that appear on slide 1 of each 3-slide subdeck.

## Slide 7: [Lab] Wind – [WBS # - Project Title] Project Modification Tracking
Aprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes
Date Mod was Approved in the AOP | Name (Lab or HQ staff) | Please provide as much information here regarding the need for the modification (Why requested, expected outcome, project impacts, financial impacts, scope changes, etc.) | +/- $500k, etc. | Please summarize any milestone changes
A modification slide should be completed for EVERY project that receives an AOP modification (increase in project funding, decrease in funding, change in project scope, etc.), and should be inserted before the Project Snapshot Slide of the modified project.
If there are no modifications to your project, please “hide” this slide for use later, if necessary.
This is NOT modification request form. Any modifications should be discussed with the appropriate HQ team lead.
This form is NOT required for new projects added mid-year.

## Slide 8: [Lab] Wind - [WBS # - Project Title] FY18 Q[X] Project Overview
Project Attributes
Budget
Total: $150,000 (Carryover: $50k , 2018 Budget Authority: $100k)
Project PI
Dana D. Science DDSci@NL.com 213-123-4567
DOE Lead
Pat Q. Fed Pfed@ee.url.gov 202-123-1234
Key Personnel
Names Emails
Project Summary
Summarize from AOP
Project Objective & Impact
Summarize from AOP

## Slide 9: [Lab] Wind - [WBS # - Project Title] FY18 Q[X] Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Comments justifying the assigned Issue Category should be clear enough that someone with no knowledge of the project can understand why the category was selected.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: HQ – Funding Delay/Rebalance
Mil. | Q1 | Schedule is on track – quarterly milestone/deliverable met on time.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: n/a
If you have a YELLOW or RED stoplight for Financials or Milestones, please provide a *detailed* explanation in the comments area – AND the steps you are taking to overcome the issue.

## Slide 10: Lab [Program] - [WBS # - Project Title] FY18 Q[X] Project Financial Status
Project Financials (FY19 Budget Authority: $______; FY18 Beginning Uncosteds: $___)
Subcontracts/Commitments: Brief Description of purpose, amount committed, expected timeframe for invoicing/spending committed funds. (Ex: $75k subcontract to Spacely Sprockets for one Cog due in Q3 FY17. Expected subcontract invoicing avg $7.5k per month from Jan. 2019 – June 2019)
Chart: 
Uncosted & Uncommitted Funds | 605445 | 0 | 0 | 0 | 0
Total Funding Level (Cum.) | 955445 | 955445 | 955445 | 955445 | 955445
FY2016 Funding Received (Cum.) | 605445 | 605445 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 161620 | 361048 | 549874 | 754700
Actual Accrued or Invoiced Costs (Cum.) | 0 | #N/A | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | #N/A | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 11: Lab [Program] - [WBS # - Project Title] FY18 Q[X] Project Milestone Status
Project Milestones (Add additional Rows for milestones if you have multiple milestones for a given quarter) If a project has multiple milestones for a given quarter (due to multiple tasks or otherwise), the stoplight determination for the project should reflect the POOREST performing milestone in that quarter. E.g. – If a project has four Q1 milestones, 3 green and 1 red, the milestone status for the overall project should be red. If more than one milestone is yellow or red, the Issue Category assigned to the project should represent the GREATEST issue affecting the project overall. | Percent Complete | Date Complete
GO/NO-GO Milestone: List it separately at the top, with description, and Due Date |  | 
FY18 Qx: Description (if necessary) |  | 
FY19 Q1 Project Milestone Description: If Milestones are modified from the original AOP, please indicate milestone modifications in RED text. |  | 
FY19 Q2 Project Milestone Description: |  | 
FY19 Q3 Project Milestone Description: |  | 
FY19 Q4 Project Milestone Description: |  | 
Please indicate here what TYPE of milestone (SMART, Progress Measure)

## Slide 12: Lab [Program] - [WBS # - Project Title] FY18 Q[X] Accomplishments & Outlook
Work accomplished this quarter: Highlight major work accomplishments (please add another slide to the deck if you need extra space for this description) Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content)
90-Day Outlook: Anticipated work for next quarter (please add another slide to the deck if you need extra space for this description) Upcoming Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content, etc.)