## Slide 1: NREL Wind – 1.3 - Atmosphere to Electrons (A2e) FY20 Q1 Project Status Overview
Project | Financial Status | Schedule/ Milestones
1.3.1.402 - WFIP II Extended Analysis |  | 
1.3.2.401 - MMC - Model Development & Validation* |  | 
1.3.3.401 - High-Fidelity Modeling* |  | 
1.3.3.402 - Energy Research and Forecast Modeling |  | 
1.3.4.401 - Rotor Wake Measurements & Predictions for Validation* |  | 
1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control |  | 
1.3.4.404 - American Wake Experiment (AWAKEN) |  | 
1.3.5.401 - Advanced Flow Control Science for Wind Plants |  | 
1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control |  | 
1.3.6.401 - Systems Engineering & Optimization |  | 
1.3.6.403 - Modeling and Validation for Offshore Wind |  | 
  1.3.2.401 (PNNL – Designated Reporting Lab)
  1.3.4.401 (NREL – Designated Reporting Lab)
** Slides included separately as a Multi-Lab Project Report:
  1.3.1.401 (PNNL – Designated Reporting Lab)
  1.3.3.401 (NREL – Designated Reporting Lab)
Notes: There should only be ONE WBS overview slide per WBS Deck, summarizing the WBS Status stoplights that appear on slide 1 of each 3-slide subdeck.

## Slide 2: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 3: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY20 Q1 Project Overview
Project Attributes
Budget
Total: $387,814 (Carryover: $137,814, 2020 Budget Authority: $250,000)
Project PI
Caroline Draxl caroline.draxl@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Caroline Draxl
Project Summary
Through WFIP2, significant forecast improvements were made by improving how numerical weather predictions (NWP) model treat complex terrain, vertical mixing between the surface and the upper atmosphere, and the impact of turbulence in the horizontal as well as vertical. Several of these have been included in the recent release of NOAA's current operational weather forecast model. However, there are other known significant sources of turbine-height forecast error that were beyond the scope of the planned WFIP2 analysis, such as errors arising within the NWP models from the land-surface models (LSMs) and the treatment of clouds. These sources of error can be addressed with additional simulations and by making use of the extensive data set collected during WFIP2.
Project Objective & Impact
The WFIP 2 dataset is a unique resource in complex terrain owing both to the extent of observations over many atmospheric scales and more than a full year of continuous measurements. We propose to use this dataset in new and expanded analyses to improve forecast accuracy through developing additional improvements to the model physics and wind power forecasting techniques. New analyses will focus on improving the LSM and cloud parameterizations in the forecast models. Additional development will build on WFIP2 progress in mathematically describing horizontal variability of turbulence and improved numerical treatment of complex topography. Methods of uncertainty quantification will be used to understand key model sensitivities to LSM and cloud parameters as well as to define overall uncertainties in improved model forecasts. Knowledge gained will be transferred, in collaboration with NOAA, to the National Weather Service’s foundational weather forecast models. Overall Project Goals and Objectives ● Evaluation and improvement of the representation of boundary-layer turbulence and surface energy exchange ● Improved understanding of model treatment of clouds on turbine-level winds ● Further improvements to model representations of horizontal variability ● Quantification of model uncertainties and application of formal verification and validation methods to model improvements

## Slide 4: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 17% underspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 5: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $250,000; FY20 Beginning Uncosteds: $137,814)
Subcontracts/Commitments:
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 137814 | 118710 | 0 | 0 | 0
Total Funding Level (Cum.) | 387814 | 387814 | 387814 | 387814 | 387814
FY20 Funding Received (Cum.) | 137814 | 179480 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 73506 | 140783 | 230171 | 310851
Actual Accrued or Invoiced Costs (Cum.) | 0 | 60679 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 60770 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 6: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: Selection of case study to validate improvements in the HRRR. |  | 
Q2: Submit journal paper about the impact of mountain waves on wind energy. |  | 
Q3: In collaboration with PNNL, deliver benchmark data set to the international community through IEA wind task 36. |  | 
Q4: Annual (SMART) Milestone: Deliver a joint report to DOE describing collaborative progress with other labs in FY20. |  | 
Q4: Report documenting the impact of Land Surface Models (LSM) on hub-height winds, including recommendations for improvements to the LSM and surface layer schemes. |  | 

## Slide 7: NREL Wind – 1.3.1.402 - WFIP II Extended Analysis FY20 Q1 Project Milestone Status
Work accomplished this quarter: NREL Public Outreach/Industry Engagement:
90-Day Outlook: NREL Selection of a case study to validate improvements in the HRRR. Work towards a journal publication of “Mountain waves impact wind energy” Work towards Q4 milestone report documenting the impact of Land Surface Models (LSM) on hub-height winds, including recommendations for improvements to the LSM and surface layer schemes. Invited talk at AGU in San Francisco in December, which will include an overview of WFIP 2 Upcoming Public Outreach/Industry Engagement:

## Slide 8: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 9: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation FY20 Q1 Project Overview
Project Attributes
Budget
Total: $783,502 (Carryover: $158,502, 2020 Budget Authority: $625,000)
Project PI
Overall PI: Sue Haupt (NCAR) haupt@ucar.edu 303-497-2763 NREL PI: Matt Churchfield matt.churchfield@nrel.gov 303-702-0890
DOE Lead
Mike Derby Michael.Derby@ee.doe.gov 202-586-6830
Key Personnel
Project Summary
Coupling mesoscale (grid spacing on the order of kilometers) and microscale (grid spacing on the order of meters to tens of meters) models is an important step forward for the wind power industry. New techniques and tools are needed to better understand the turbulent flow into and within the wind plant, which impacts energy transfer between scales, and ultimately, the amount of power. The ability to couple these scales is particularly important for non-stationary meteorological conditions (such as frontal passages, thunderstorm outflows, baroclinic systems, and low-level jets) or when considering changes of atmospheric stability associated with the diurnal cycle.
Project Objective & Impact
Apply verification and validation (V&V) techniques to the new modeling tools that are developed to ensure the accuracy of our codes and results and develop estimates of the uncertainty Improve computational performance of the coupled MMC models through the development of methods that can be used to reduce turbulence spin-up time and hence the size of computational domains Improve representation of the surface layer in microscale models to improve simulations of wind speed and shear over the rotor diameter Develop guidance for the community describing the best ways to couple mesoscale and microscale models, including specific spatial scales at which the handoff to the microscale model should occur Prepare documentation and a suite of software tools that can be used across the community Transition MMC research to the offshore environment.

## Slide 10: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 64% underspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 11: NREL Wind - 1.3.2.401 - MMC - Model Development & Validation FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $625,000; FY20 Beginning Uncosteds: $158,502)
Subcontracts/Commitments:
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 158502 | 171033 | 0 | 0 | 0
Total Funding Level (Cum.) | 783502 | 783502 | 783502 | 783502 | 783502
FY20 Funding Received (Cum.) | 158502 | 262668 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 256299 | 374073 | 501170 | 626088
Actual Accrued or Invoiced Costs (Cum.) | 0 | 91635 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 91635 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 12: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: By December 31, 2019, Submit an annual report to DOE summarizing annual progress during FY19 including: benchmark cases, metrics, baseline uncoupled runs, targets for improvements relevant to wind plants, and optimal inflow perturbation methods (Common milestone with LLNL, NREL, and PNNL in collaboration with NCAR). |  | 
Q2: By March 31, 2020, NREL will advance atmospheric gravity wave treatment methods to include complex situations with arbitrary terrain, realistic turbulent inflow, and wind turbines. |  | 
Q3: By June 30, 2020, NREL and PNNL will provide short report outlining potential offshore data sets and case studies that could be used by the MMC team (Common Milestone with PNNL). |  | 
Q4: By Sept 30, 2020, NREL will assess the impact of MMC on simulations of the Peetz Table Wind Farm. Comparison between simulating Peetz Table Wind Farm using canonical methods versus using MMC methods will be made. (This work will be in collaboration with the A2e Wake Dynamics project, and will relate to the A2e NREL Wake Dynamics Q3 milestone.) |  | 

## Slide 13: NREL Wind – 1.3.2.401 - MMC - Model Development & Validation FY20 Q1 Project Milestone Status
Work accomplished this quarter: Public Outreach/Industry Engagement:
90-Day Outlook: Upcoming Public Outreach/Industry Engagement:

## Slide 14: NREL Wind – 1.3.3.401 - High-Fidelity Modeling Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 15: NREL Wind – 1.3.3.401 - High-Fidelity Modeling FY20 Q1 Project Overview
Project Attributes
Budget
Total: $1,895,350 (Carryover: $420,350, 2020 Budget Authority: $1,475,000)
Project PI
Michael Sprague michael.a.sprague@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Project Summary
Summarize from AOP
Project Objective & Impact
Summarize from AOP

## Slide 16: NREL Wind – 1.3.3.401 - High-Fidelity Modeling FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 18% overspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 17: NREL Wind - 1.3.3.401 - High-Fidelity Modeling FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $1,475,000; FY20 Beginning Uncosteds: $420,350)
Subcontracts/Commitments:
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 420350 | 201013 | 0 | 0 | 0
Total Funding Level (Cum.) | 1895350 | 1895350 | 1895350 | 1895350 | 1895350
FY20 Funding Received (Cum.) | 420350 | 666184 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 356742 | 693527 | 1115745 | 1517998
Actual Accrued or Invoiced Costs (Cum.) | 0 | 420969 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 465171 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 18: NREL Wind – 1.3.3.401 - High-Fidelity Modeling FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1 (NREL/SNL): Implement in Nalu-Wind advanced actuator lines and document the performance of the new capability relative to a “standard” actuator-line method for uniform inflow (e.g., the Sorensen and Shen (2002) model), and blade-resolved simulations established in FY19 Q4. The NREL Phase VI will be the test case and both yawed and unyawed configurations will be examined. The comparison quantities of interest will be blade loads, but there will also be an examination of tip vortices and their sensitivity to the underlying actuator-line model. This milestone establishes a necessary mid-fidelity capability requirement that will enable validation of the highest-fidelity models, while accelerating the advancement of mid-fidelity models from high-fidelity modeling results. |  | 
Q2 (NREL/SNL): Enhance Nalu-Wind’s actuator disc model through hardening, documenting, stress-testing, verifying, and validating. Existing workflows will be improved by reducing the data output stream, and by making the analysis capabilities more modular and generally better. These model capabilities are needed by other WETO research areas, namely Wake Dynamics, AWAKEN, Controls, and VV&UQ. |  | 
Q3 (NREL): Validate the BeamDyn nonlinear-finite-element blade model for long, flexible blades (curved and straight) with bend-twist coupling by comparing results against resolved nonlinear shell finite-element models. The comparison will be done in the absence of fluid-structure-interaction effects in order to understand the potential limitations of a beam-modeling approach. Also studied will be the sensitivity of results to certain modeling approaches, e.g., model refinement and the choice of reference line for curved blades. Quantities of interest will be blade displacement and rotation responses (static and dynamic). |  | 
Q3 (NREL/SNL): Perform a comparison of the aerodynamic and structural loads under turbulent inflow conditions for the blade-resolved Nalu-Wind simulations of the NM80 rotor (IEA Task 29 benchmark case), for which turbulence is generated in two different ways: 1. Synthetic turbulence from a Mann model introduced as source terms within the computational domain; 2. A full precursor simulation where the ABL profile and turbulence is generated in using the standard process in Nalu-Wind. Where appropriate, the study will use the benchmark conditions provided by the IEA 29 working group and attempt comparisons with field data for the cases that have been provided. The study will include additional cases to explore the sensitivity of turbine performance and loads to fully resolved ABL inflow conditions as compared to synthetic homogeneous turbulent inflow. This milestone supports the first MW-scale full-turbine validation problem for Nalu-Wind/OpenFAST as defined by the HFM Benchmark Working Group. |  | 
Q4 (NREL/SNL): Implement in Nalu-Wind the boundary conditions and gravity-wave-damping features necessary for simulating ABL flows in complex terrain as recently demonstrated in SOWFA. As detailed by the HFM Benchmark Working Group Plan, perform code-to-code ABL-simulation comparisons under stable and unstable conditions for flat terrain and perform the first complex-terrain benchmark problem. |  | 

## Slide 19: NREL Wind – 1.3.3.401 - High-Fidelity Modeling FY20 Q1 Project Milestone Status
Work accomplished this quarter: Public Outreach/Industry Engagement:
90-Day Outlook: Upcoming Public Outreach/Industry Engagement:

## Slide 20: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 21: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling FY20 Q1 Project Overview
Project Attributes
Budget
Total: $56,173 (Carryover: $6,173, 2020 Budget Authority: $50,000)
Project PI
Eliot Quon eliot.quon@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Project Summary
Many wind energy developments are plagued by underperformance and reliability issues, due to inadequacy of physics and computational capabilities within existing simulation codes. The Energy Research and Forecasting (ERF) will be a next-generation fluid dynamics simulation code targeting larger scales of atmospheric flows, capable of providing accurate meteorological and environmental forcings for high-fidelity models of the wind plant environment.
Project Objective & Impact
ERF will improve upon the established Weather Research and Forecasting (WRF) model, optimizing the code for modern HPC infrastructures and enhancing parallel scalability. This will permit more efficient simulation of larger nested domains with higher resolution. ERF will eliminate simulation bottlenecks that were in WRF, such as initialization and file I/O, and address the shortcomings of WRF’s load balancing and downscaling algorithms, numerical methods, and physics parameterizations. ERF will enable seamless coupling with microscale solvers such as Nalu-Wind by implementing physics modules and algorithms developed in the WETO Mesoscale-to-Microscale Coupling project, thereby facilitating high-fidelity multiscale wind plant simulations.

## Slide 22: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 60% underspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 23: NREL Wind - 1.3.3.402 - Energy Research and Forecast Modeling FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $50,000; FY20 Beginning Uncosteds: $6,173)
Subcontracts/Commitments:
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 6173 | 33744 | 0 | 0 | 0
Total Funding Level (Cum.) | 56173 | 56173 | 56173 | 56173 | 56173
FY20 Funding Received (Cum.) | 6173 | 39508 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 14524 | 26065 | 48220 | 56173
Actual Accrued or Invoiced Costs (Cum.) | 0 | 5764 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 5764 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 24: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Submit workshop summary to DOE by December 31, 2019.Summarize workshop proceedings and short-term/long-term code development plans in a report to the DOE. This is a joint milestone between ANL, LLNL, PNNL, and NREL. |  | 
Q2: Identify requirements for software testing by March 31, 2020.Identify hardware requirements for a dedicated software testing platform, leveraging experiences from Nalu-Wind. The dedicated system will enable daily testing for software quality assurance. |  | 
Q3: Deploy software testing platform by June 30, 2020.Deploy automated testing platform on ERF-dedicated system(s) for software quality assurance using, for example, the open-source, web-based CDash software testing server. If funding is unavailable for ERF-dedicated hardware in FY20, automated testing will rely on available DOE LCF resources. |  | 
Q4: Establish reference data on testing system(s) by September 30, 2020.Evaluate existing regression test cases, e.g., from recent studies performed in the A2e mesoscale-to-microscale coupling project, for a variety of computational environments on the new system(s) to establish reference datasets. |  | 

## Slide 25: NREL Wind – 1.3.3.402 - Energy Research and Forecast Modeling FY20 Q1 Project Milestone Status
Work accomplished this quarter: Public Outreach/Industry Engagement:
90-Day Outlook: Meet with NREL researchers to establish relationship between ERF and the existing High-Fidelity Modeling (HFM) project. Plan meeting agenda for upcoming kick-off meeting and workshop, set for Oct 30-31, 2019. Together with ANL, LLNL, and PNNL, summarize workshop proceedings and short-term/long-term code development plans in a report. Establish repository access protocols and standards for ERF code development. Develop plan for software quality assurance, based on past experiences with HFM. This plan will include identification of hardware requirements and strategies for software testing given different hardware and high-performance computing resource availability scenarios. Upcoming Public Outreach/Industry Engagement:

## Slide 26: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 27: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY20 Q1 Project Overview
Project Attributes
Budget
Total: $2,623,832 (Carryover: $523,832, 2020 Budget Authority: $2,100,000)
Project PI
Paula Doubrawa Paula.doubrawa@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Project Summary
Summarize from AOP
Project Objective & Impact
Summarize from AOP

## Slide 28: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 45% overspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 29: NREL Wind - 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $2,100,000; FY20 Beginning Uncosteds: $523,832)
Subcontracts/Commitments:
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 523832 | 65712 | 0 | 0 | 0
Total Funding Level (Cum.) | 2623832 | 2623832 | 2623832 | 2623832 | 2623832
FY20 Funding Received (Cum.) | 523832 | 715499 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 370608 | 765944 | 1799294 | 2097008
Actual Accrued or Invoiced Costs (Cum.) | 0 | 538739 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 649787 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 30: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: Wind plant model validation focused on deep-array effects. By December 31, 2019, NREL will analyze an existing wind plant dataset to validate the ability of current wind plant models to simulate deep-array effects for a broad range of operational and atmospheric conditions. The results of this study will be submitted as an abstract for publication and presentation at the TORQUE 2020 conference. These results will inform and support the improvement of FLORIS performed in the A2e Controls project during Q2. |  | 
Q2: Development and validation of plant-level solver for curled wake model. By March 31, 2020, NREL will expand the curled wake model by developing (i) a plant-level solver and (ii) an improved turbulence model that includes atmospheric stratification effects. The validation will leverage the field and simulation data analyzed for the Q1 milestone. This model will also facilitate FAST.Farm improvements planned in the ISDA-OSW project. |  | 
Q3: High-fidelity validation study using Peetz measurements. By June 30, 2020, NREL will complete the first validation study of high-fidelity models against experimental data from the Peetz Table Phase II experiment. Results will be presented at the TORQUE 2020 conference. This work will be in collaboration with the A2e MMC NREL project, and will relate to the A2e MMC NREL Q4 milestone. |  | 
Q4: Assessment of experimental data needs for high-fidelity model validation. By September 30, 2020, NREL and SNL will jointly author a report that (i) presents a detailed gaps analysis in terms of observational data needed to validate high-fidelity simulations of large, flexible wind turbines and their wakes when operating in aligned and misaligned states, and (ii) proposes field campaign solutions to address these needs during FY21-FY23. |  | 

## Slide 31: NREL Wind – 1.3.4.401 - Rotor Wake Measurements & Predictions for Validation FY20 Q1 Project Milestone Status
Work accomplished this quarter: Highlight major work accomplishments (please add another slide to the deck if you need extra space for this description) Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content)
90-Day Outlook: Anticipated work for next quarter (please add another slide to the deck if you need extra space for this description) Upcoming Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content, etc.)

## Slide 32: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 33: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Overview
Project Attributes
Budget
Total: $388,517 (Carryover: $388,517, 2020 Budget Authority: $0)
Project PI
Nicholas Hamilton nicholas.hamilton@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Nicholas Hamilton
Project Summary
The extent to which modern wind plant control strategies induce additional aeroacoustic emissions from additional separation and other flow interaction dynamic effects is not known, and may have a significant impact on future wind plant development and wind turbine siting. Off-nominal rotor control by prescribed yaw misalignment is expected to induce periodic flow separation locally along the rotor blades and change the aerodynamic interaction with the local flow field. Given public concerns about wind turbine noise and the need for observational data required for regulators to establish noise restrictions, potential acoustic emissions resulting from active control must be understood prior to commercial deployment and the development of practical noise reduction methods and technology. Additional downstream acoustic propagation effects introduced by active yaw and or thrust control must be investigated and understood for modern wind plant control strategies to be successfully implemented at the utility scale.
Project Objective & Impact
Aeroacoustics project objectives are focused on quantifying the additional acoustic emissions introduced by implementing modern wind turbine and wind plant control strategies. Acoustic noise produced by wind turbines is one of the limiting factors on their operation and one of the constraints placed on development of wind plants. Specific FY19 and FY20 objectives are to: Experimentally quantify the aeroacoustic emissions of a utility scale wind turbine operating under yawed conditions. Determine the nature of the changes to the overall sound pressure level directivity under the influence of yaw misalignment. Update and validate aeroacoustic modeling software to integrate into current OpenFAST framework against observational data collected experimentally. Disseminate findings of aeroacoustic field observations for a utility-scale wind turbine operating under prescribed yaw offsets though peer-reviewed journal publications

## Slide 34: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 71% underspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 35: NREL Wind - 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $0; FY20 Beginning Uncosteds: $388,517)
Subcontracts/Commitments: Acoustic instrumentation will be acquired to make experimental observations in support of the project goals and milestones. FY19 spending on instrumentation (originally estimated at $40k) has been delayed to ensure that the correct instrumentation is acquired. FY19 and FY20 funds will be combined to acquire all necessary equipment in FY20 Q1, totaling $90k. Suppliers include Brüel & Kjær (for microphones, preamplifiers, signal conditioners, ~$60k), National Instruments (for data acquisition platform ~$12k), Delta (for data processing software ~$6k), cabling/microphone soundboards/hardware (~$10k)
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 388517 | 293248 | 0 | 0 | 0
Total Funding Level (Cum.) | 388517 | 388517 | 388517 | 388517 | 388517
FY20 Funding Received (Cum.) | 388517 | 388517 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 170532 | 249832 | 319459 | 388517
Actual Accrued or Invoiced Costs (Cum.) | 0 | 49379 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 95269 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 36: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: Specify instrumentation needs to make point measurements for time- and frequency-domain assessment of aeroacoustic emissions of GE 1.5 MW wind turbine |  | 
Q2: Deploy instrumentation around DOE-owned GE 1.5 MW wind turbine at NREL Flatirons campus and begin data acquisition, quality assurance, and quality control processes for audio data. |  | 
Q3: Complete technical report on aeroacoustic code verifications using the updated framework of aeroacoustics module and physics models to interface with NREL modeling tools. |  | 
Q4: Submit article to peer-reviewed scientific publication detailing the aeroacoustic tests performed as part of the project and quantifying the changes in acoustic emission introduced by operating a utility-scale wind turbine in yawed conditions. |  | 

## Slide 37: NREL Wind – 1.3.4.403 - Aeroacoustic Assessment of Wind Plant Control FY20 Q1 Project Milestone Status
Work accomplished this quarter: Project officially started in FY19 Q4, including: Public Outreach/Industry Engagement:
90-Day Outlook: FY20 Q1 will be focused on specifying instrumentation and equipment needs to support the test plan developed in FY19 Q4. The detailed schedule for observations will be refined as instrumentation is brought on board, calibrated and tested on site. Any modifications to the test plan as required by outside constraints (sensor placement, site access, coordination with other research) will be factored into and incorporated into the working test plan document. Upcoming Public Outreach/Industry Engagement: Continued engagement with the wind turbine aeroacoustics research community will inform instrument specification and acquisition and avoid pitfalls in data collection and processing. No public dissemination of test results is planned for the aeroacoustics project until FY20 Q3.

## Slide 38: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 39: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) FY20 Q1 Project Overview
Project Attributes
Budget
Total: $1,049,628 (Carryover: $139,628, 2020 Budget Authority: $910,000)
Project PI
Patrick Moriarty patrick.moriarty@nrel.gov
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Project Summary
Summarize from AOP
Project Objective & Impact
Summarize from AOP

## Slide 40: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 60% underspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 41: NREL Wind - 1.3.4.404 - American Wake Experiment (AWAKEN) FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $910,000; FY20 Beginning Uncosteds: $139,628)
Subcontracts/Commitments:
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 139628 | 207143 | 0 | 0 | 0
Total Funding Level (Cum.) | 1049628 | 1049628 | 1049628 | 1049628 | 1049628
FY20 Funding Received (Cum.) | 139628 | 291298 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 211923 | 403128 | 644307 | 871282
Actual Accrued or Invoiced Costs (Cum.) | 0 | 84155 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 84155 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 42: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: Submit to DOE a draft summary technical report of the AWAKEN project that will provide an overview and vision for the project and include summaries of past activities including expert elicitation meetings. |  | 
Q2: Hold experts meeting of instrumentation and modeling specialists to inform instrumentation development roadmap for the AWAKEN project. |  | 
Q3: Coordination meeting with European partners at The Science for Making Torque from Wind conference in Delft, The Netherlands. |  | 
Q4: Site selection for the AWAKEN project completed and a document describing the selection process will be sent to DOE. |  | 

## Slide 43: NREL Wind – 1.3.4.404 - American Wake Experiment (AWAKEN) FY20 Q1 Project Milestone Status
Work accomplished this quarter: Highlight major work accomplishments (please add another slide to the deck if you need extra space for this description) Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content)
90-Day Outlook: Anticipated work for next quarter (please add another slide to the deck if you need extra space for this description) Upcoming Public Outreach/Industry Engagement: (Publications, videos, presentations, photos, journal article submissions, webinars, industry round-tables, news coverage, updated web content, etc.)

## Slide 44: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 45: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY20 Q1 Project Overview
Project Attributes
Budget
Total: $1,397,156 (Carryover: $397,156, 2020 Budget Authority: $1,000,000)
Project PI
Paul Fleming Paul.fleming@nrel.gov 303-384-6918
DOE Lead
Mike Derby Michael.Derby@ee.doe.gov 202-586-6830
Key Personnel
Paul Fleming Jennifer King Alan Wright Eric Simley Christopher Bay
Project Summary
A smart plant, where the control activities of individual turbines are coordinated by a central wind farm controller, using information from each of the turbines as well as additional available sensing such as lidars, can substantially improve the performance of existing and new wind farms. Advanced flow control science for wind plants research provides the implementation strategies and methods to deliver wind plant performance improvements.
Project Objective & Impact
This project will develop the technical capabilities, methods, and approaches that enable “smart plant” control design to optimize wind plants with respect to energy capture and loads. The project will advance wind farm control-oriented modeling to include advanced vortex physics, wake interaction and energy entrainment, as well as the impact of atmospheric stability. The project will deliver new wind farm control strategies and algorithms that can manipulate underlying physical phenomenon driving performance. The project will perform field campaign and LES-based evaluation of control model and strategy effectiveness and performance. Finally it will provide a complete control model and generic strategy for implementing and evaluating strategies for offshore floating platforms.

## Slide 46: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 16% underspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 47: NREL Wind - 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $1,000,000; FY20 Beginning Uncosteds: $397,156)
Subcontracts/Commitments:
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 397156 | 145153 | 0 | 0 | 0
Total Funding Level (Cum.) | 1397156 | 1397156 | 1397156 | 1397156 | 1397156
FY20 Funding Received (Cum.) | 397156 | 563822 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 349474 | 556099 | 818319 | 1093280
Actual Accrued or Invoiced Costs (Cum.) | 0 | 294817 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 418669 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 48: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1 – Complete an openFAST-based study demonstrating the effectiveness of the generic controller to successfully control a range of floating turbine configurations, and to validate its suitability in co-optimization studies. |  | 
Q2 – Update FLORIS for large and offshore wind farms to include deep array effects, and produce report showing improved agreement with real offshore wind farm data. |  | 
Q3 – Design new full-farm wind farm control system coupling consensus control, uncertainty optimization and exploitation of vortex effects and validate improvement using high fidelity modeling simulation with SOWFA and/or Nalu. |  | 
Q4 – Use latest FLORIS model and control algorithms to perform optimization studies to assess the benefits of wind farm control given advanced engineering models and control. |  | 

## Slide 49: NREL Wind – 1.3.5.401 - Advanced Flow Control Science for Wind Plants FY20 Q1 Project Milestone Status
Work accomplished this quarter: Public Outreach/Industry Engagement:
90-Day Outlook: Study will be completed of new generic controller applied to a variety of offshore floating systems Collaboratively with wake steering, investigate the inclusion of important additional physical effects into FLORIS including deep-array effects and near-wake specific models. Comparison with offshore SCADA data will be used to assess various possible corrections Upcoming Public Outreach/Industry Engagement: Expect to submit two journal papers in near future, one on further physics improvements in FLORIS and an additional journal paper (together with wake dynamics) detailing results of wake steering campaign at Peetz and comparison with new FLORIS models Will begin preparing a report/journal or conference paper on results of IEA Wind topical expert’s meeting and expert elicitation

## Slide 50: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 51: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY20 Q1 Project Overview
Project Attributes
Budget
Total: $249,999 (Carryover: $249,999, 2020 Budget Authority: $0)
Project PI
Jennifer King Jennifer.King@nrel.gov 303-384-7086
DOE Lead
Mike Derby Michael.Derby@ee.doe.gov 202-586-6830
Key Personnel
Paul Fleming Jennifer King Alan Wright Eric Simley Christopher Bay
Project Summary
Wind turbines in a wind farm typically operate individually to maximize their own performance without explicitly taking into account information from nearby turbines. To enable cooperation to achieve farm-level objectives, turbines will need to use information from nearby turbines to optimize performance, ensure resiliency when sensors fail, and adapt to changing local conditions.
Project Objective & Impact
The objective of this project is to deploy a Collective Consensus Controller for Performance Optimization (C3PO), on a utility-scale wind farm in the field to demonstrate the potential power performance gain in a wind farm. This project will be done in coordination with an industry partner, Renewable Energy Systems (RES). C3PO is a cooperative wind farm controller that incorporates information from local sensors in real-time to better align turbines to the prevailing wind direction to improve performance of individual turbines.

## Slide 52: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 92% underspent.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 53: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $0; FY20 Beginning Uncosteds: $249,999)
Subcontracts/Commitments:
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 249999 | 208721 | 0 | 0 | 0
Total Funding Level (Cum.) | 249999 | 249999 | 249999 | 249999 | 249999
FY20 Funding Received (Cum.) | 249999 | 249999 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 24211 | 47003 | 75876 | 103326
Actual Accrued or Invoiced Costs (Cum.) | 0 | 1984 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 41278 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 54: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1 – NREL will complete baseline collection of data from multiple sites by 12/31/2019. |  | 
Q2 – NREL will use C3PO technology to perform analysis of SCADA data from approximately five wind farms in RES’s portfolio, NREL will deliver a report of the analysis to RES by March 31, 2020 |  | 
Q3 – NREL will develop a test plan for how to implement the C3PO technology and what additional hardware/software needs to be installed, by June 30, 2020. |  | 
Q4 - NREL will provide a detailed report on the implementation approach with expected gains to RES by September 30, 2020. |  | 

## Slide 55: NREL Wind – 1.3.5.402 - Enabling Autonomous Wind Plants through Consensus Control FY20 Q1 Project Milestone Status
Work accomplished this quarter: Public Outreach/Industry Engagement:
90-Day Outlook: NREL will complete baseline collection of data from multiple sites by 12/31/2019. This data will be uploaded to internal databases that will allow for easy analysis with respect to the collective consensus control software as well as comparison between the wind farms. Upcoming Public Outreach/Industry Engagement: NREL will begin writing a report for RES on the performance of collective consensus control at their different wind farms.

## Slide 56: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 57: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization FY20 Q1 Project Overview
Project Attributes
Budget
Total: $1,015,344 (Carryover: $235,344, 2020 Budget Authority: $780,000)
Project PI
Garrett Barter garrett.barter@nrel.gov 303-384-7102
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Garrett Barter Jennifer King Ryan King Pietro Bortolotti Peter Graf Evan Gaertner
Project Summary
The SEO initiative develops an analysis platform and research capability to capture important system interactions to achieve a better understanding of how to improve system-level performance and achieve system-level cost reductions. The effort incorporates advances in computational algorithms, simulation methods, physics-based improvements, cost and performance modules to assess new technology opportunities and advance the state-of-the-art and best practices in multi-disciplinary design, analysis and optimization (MDAO) for wind energy applications.
Project Objective & Impact
The objectives of SEO include: Advance the state-of-the-art in MDAO for wind energy applications in terms of enabling wind turbine and plant design that 1) incorporates increased system scope to investigate trade-offs in a variety of aspects of system design and operation, 2) incorporates models of increased fidelity to allow more realistic and accurate representation of the system in the upfront optimization process, and 3) incorporates more sophisticated workflows (i.e., multi-level, multi-fidelity optimization under uncertainty) for more efficient and robust system design. Demonstrate the value of MDAO for improving overall wind turbine and plant performance and cost through a series of case studies. Promote adoption of MDAO and related techniques by industry through demonstration of value and publication of best practices.

## Slide 58: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is on track.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:
Mil. | Q1 | 
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category:

## Slide 59: NREL Wind - 1.3.6.401 - Systems Engineering & Optimization FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $780,000; FY20 Beginning Uncosteds: $235,344)
Subcontracts/Commitments:
BYU subcontract with Prof. Andrew Ning
CU subcontract with Prof. Peter Hamlington
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 235344 | -60178 | 0 | 0 | 0
Total Funding Level (Cum.) | 1015344 | 1015344 | 1015344 | 1015344 | 1015344
FY20 Funding Received (Cum.) | 235344 | 365344 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 243626 | 420474 | 645150 | 797072
Actual Accrued or Invoiced Costs (Cum.) | 0 | 263283 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 425522 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 60: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: Complete and submit conference papers for AIAA SciTech 2019 on uncertainty quantification, optimization under uncertainty, and the application of statistical methods for turbulent inflow modeling within rotor design loop. (December 31, 2019) | 100% | 12/31/2019
Q2 Demonstration of unsteady solver capabilities in WindSE such that “controllability” can be studied and measured in a wind plant by the end of FY20 Q2 (March 31, 2020). | 50% | 
Q3: A draft paper detailing the modeling approach and results when accounting for reliability. The paper will be ready for peer-review by the end of FY20 Q3 (June 30, 2020). | 25% | 
Q4: A draft paper detailing the design approach and results when customizing a wind plant for best wake steering performance. The paper will be ready for peer-review by the end of FY20 Q4 (September 30, 2020). |  | 

## Slide 61: NREL Wind – 1.3.6.401 - Systems Engineering & Optimization FY20 Q1 Project Milestone Status
Work accomplished this quarter: Completed AIAA papers related to 1) usage of Importance Sampling to estimate extreme loads within a design loop 2) Multiple collaborative papers with Sandia on UQ methods applied to wind energy Collaborated on the design of the 15MW Reference Wind Turbine Submitted multiple abstracts to the TORQUE conference Public Outreach/Industry Engagement: Attended the IEA Wind Task 37 Meeting and the 2019 Systems Engineering Workshop hosted by CENER in Pamplona, Spain. Presented work related to the 15MW Reference Turbine, a common ontology for blade systems engineering, and a tutorial for WISDEM Presented two papers at NAWEA WindTech: 1) Layout optimization in complex terrain, 2) Loads-aware layout optimization
90-Day Outlook: Finish unsteady solver for WindSE and calculate plant “controllability” Complete FAST.Farm runs of plant flow that will serve as basis for layout optimization for reliability surrogate model Complete TORQUE papers that are awarded a podium presentation Collaborate on LCOE calculation for Lightweight Drivetrain FOA 1981 awardees Upcoming Public Outreach/Industry Engagement: Present AIAA papers related to 1) usage of Importance Sampling to estimate extreme loads within a design loop 2) Multiple collaborative papers with Sandia on UQ methods applied to wind energy

## Slide 62: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind Project Modification Tracking
Apprv. Date | Requested By | Detailed Reason for Modification | Budget Change | Milestone Changes

## Slide 63: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY20 Q1 Project Overview
Project Attributes
Budget
Total: $1,444,254 (Carryover: $404,254, 2020 Budget Authority: $1,040,000)
Project PI
Amy Robertson Amy.Robertson@nrel.gov 303-384-7157 Jason Jonkman Jason.Jonkman@nrel.gov 303-384-7026
DOE Lead
Michael Derby michael.derby@ee.doe.gov 202-586-6830
Key Personnel
Roger Bergua Emmanuel Branlard Matthew Hall Tony Martinez Andy Platt Kelsey Shaler Toan Tranh Lu Wang
Project Summary
This Integrated Systems Design and Analysis – Modeling and Validation for Offshore Wind (ISDA-OSW) project enables the development of advanced offshore wind-plant technology by leveraging knowledge and data to improve physics-based engineering design competence and tools at the wind turbine, offshore support structure, and full wind-plant levels collaboratively with the wind energy community. This project helps to advance innovative wind technologies to commercial maturity by improving, verifying, and validating physics-based engineering tools used for designing wind systems with high-quality datasets and higher-fidelity model results under a variety of conditions. Verification and validation activities (V&V) assess the accuracy of the modeling tools, provide a better understanding of their uncertainties, identify needed areas of improvement, and increase their acceptance within industry and wind research communities. Collaboration with the wind energy community happens through engagement in international V&V collaboratives through the International Energy Agency (IEA) Technology Collaboration Programme and related research projects among research laboratories, academia, and industry. Many of the land-based design and modeling challenges are a subset of those from OSW, so while the focus is on OSW, the project also supports land-based technology advancement. Moreover, the project uses some data from land-based systems to improve OSW design competence and tools.
Project Objectives & Impact
The goal of this project is to improve offshore wind physics-based engineering design competence and tools to enable the advancement of innovative wind technologies to commercial maturity. This goal will be achieved through the following project objectives: • Quantitively understand the accuracy, applicability, limitations, and uncertainty in offshore wind physics-based engineering tools needed to enable the development of advanced wind technology through comparisons to HFM and experimental data. • Improve the physics of offshore wind engineering tools for wind turbines, offshore support structures, and wind plants to expand the tools’ applicability where limitations hinder technology advancement. • Understand parameters driving the design of offshore wind systems. • Develop an iterative, multi-fidelity, probabilistic design process for offshore wind turbines and wind plants needed to enable cost-effective and reliable technology innovations. • Engage in international V&V collaboratives and related wind research projects among research laboratories, academia, and industry to broaden U.S. knowledge.

## Slide 64: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY20 Q1 Project Performance Overview
Project Status |  | 
Cat. | St. | Comments
Fin. | Q1 | Project is 49% underspent. Under-spending is due to not having costed a purchase order associated with the validation campaign at Texas A&M University. Also, the replacement of employee, Fabian Wendt, was delayed due to VISA issues with the new hire, Roger Bergua. Roger has now started at NREL at the beginning of January.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: Lab - External Project Partner
Mil. | Q1 | Schedule is on track – quarterly milestone/deliverable met on time. The FY 2019 Q4 milestone regarding the submission of a journal manuscript on the development and validation of FAST.Farm has been completed in Q1 of FY 2020. The manuscript was submitted to the Wind Energy journal for review and publication is expected in FY 2020.
 | Q2 | 
 | Q3 | 
 | Q4 | 
 |  | Category: N/A

## Slide 65: NREL Wind - 1.3.6.403 - Modeling and Validation for Offshore Wind FY20 Q1 Project Financial Status
Project Financials (FY20 Budget Authority: $1,040,000; FY20 Beginning Uncosteds: $404,254)
Subcontracts/Commitments:
A purchase order worth $301K has been signed with Texas A&M Engineering Experiment Station for the work effort titled “Component-Level Hydrodynamic Validation Campaign for Floating Wind”. The term of the PO is from October 2019.
Chart: 
| 0 | FY20 Q1 | FY20 Q2 | FY20 Q3 | FY20 Q4
Uncosted & Uncommitted Funds | 404254 | 312530 | 0 | 0 | 0
Total Funding Level (Cum.) | 1444254 | 1444254 | 1444254 | 1444254 | 1444254
FY20 Funding Received (Cum.) | 404254 | 577587 | #N/A | #N/A | #N/A
Projected Recipient Spend Plan (Cum.) | 0 | 455498 | 746096 | 1130556 | 1444254
Actual Accrued or Invoiced Costs (Cum.) | 0 | 233457 | #N/A | #N/A | #N/A
Actuals + Commitments (Cum) | 0 | 265057 | #N/A | #N/A | #N/A
Notes: Graphic generated by the Financial Tracking Spreadsheet

## Slide 66: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY20 Q1 Project Milestone Status
Project Milestones | Percent Complete | Date Complete
Q1: Within the IEA Wind Task 29 Aerodynamics international V&V collaborative, complete the second round of comparisons between OpenFAST’s predictions of wind turbine loads and power against other engineering-model solutions, HFM computations, and experimental data from the DanAero to be shared at the Task 29 annual meeting by December 31, 2019. | 100% | 1/17/20
Q2: Complete the IEA Wind Task 30 OC6 Phase I validation study by 03/31/20, which is focused on better understanding the under-prediction of motion/loads for a floating wind semisubmersible due to nonlinear hydrodynamics. Motion and load measurements from two scale-model tank campaigns will be compared to simulated responses provided by a variety of participants in the OC6 project. A paper summarizing the work will be developed by 03/31/20, and presented at the TORQUE 2020 conference in the summer. | 50% | 
Q3: Complete a validation of FAST.Farm’s predictions of wind turbine power and wake evolution and meandering against experimental data from three turbines from the Peetz Table wind farm and document the findings in paper to be presented at TORQUE 2020 by June 30, 2020. | 10% | 
Q4: Complete coupling of the higher-fidelity REDWIN soil/structure interaction module to OpenFAST to enable a more accurate representation of the dynamic response of fixed-bottom offshore wind turbines. A new version of OpenFAST with this capability will be released to the public by September 30, 2020. | 5% | 

## Slide 67: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY20 Q1 Project Milestone Status
Work accomplished this quarter: IEA Wind Task 30 (OC6): Bi-annual meeting of the OC6 project was held in conjunction with the IOWTC conference on Nov. 7th in Malta. The OC6 group initiated simulations across all five of the load case groups for Phase I (to be concluded in Q2). CFD subgroup started modeling a bichromatic wave case, which will focus directly on the hydrodynamic nonlinear modeling issue. Abstract submitted for presentation of the OC6 Phase I work at the TORQUE conference (which will be held in May, 2020 in Delft). New Validation Campaign: Wave calibration was completed as well as tests associated with a single cylinder. Testing will continue through Q2. Reviewed measurements and provided feedback to validation campaign. IEA Wind Task 29 (Aerodynamics) & Related Aero-Elastic V&V: Ran and submitted updated load-case simulations for aero-elastic round using OpenFAST in support of three-way V&V collaborative involving DanAero data for next Task 29 meeting in Rome in February. IEA Wind Task 31 (WakeBench), Related Wind-Plant V&V, & Model Improvements: FY 2019 Q4 milestone: submitted draft Wind Energy paper on the development of FAST.Farm and the validation of its loads predictions against HFM results from coupled SOWFA-OpenFAST. Submitted draft Wind Energy journal paper on the three-way V&V collaborative involving A2e SWiFT data within WakeBench. Attended the WakeBench meeting held in conjunction with the NAWEA / WindTech 2019 conference. Developed OpenFAST and FAST.Farm models of 5 wind turbines at the Peetz Table wind farm, identified experimental datasets and met-tower, LIDAR, and SCADA measurements for validation. Submitted a related abstract for a paper to be presented at TORQUE. Ran HFM actuator-disk simulations to study the wake response under high thrust conditions, the results of which will be used to improve the near-wake correction model in, and robustness of, FAST.Farm. Submitted a related abstract for a paper to be presented at TORQUE Sensitivity Analysis: Finalized the approach for the sensitivity assessment of engineering model predictions of loads and power for turbines in a small wind farm to variations in wind inflow and wake parameters to identify the most influential parameters. Public Outreach/Industry Engagement: Senu Sirnivas attended the bi-annual joint meeting of the CFD JIP for offshore systems. Still working on formally joining. Amy Robertson presented a paper on new bichromatic wave cases for the floating wind hydrodynamic validation campaign at IOWTC. Amy Robertson attended IECRE/TC88 Joint Working Forum on Model Validation on Oct. 14-15, 2019 in Denmark. HPC Usage: Two HPC accounts are associated with this project. The status for Q1 usage is as follows: fwta – 92,699 units used/115,000 units allocated = 81%. Underusage due to lapse in renewal of STAR-CCM+ license. isda – 7,658 units used/18,400 units allocated = 42%. Nonlinear usage between quarters expected.

## Slide 68: NREL Wind – 1.3.6.403 - Modeling and Validation for Offshore Wind FY20 Q1 Project Milestone Status
90-Day Outlook: IEA Wind Task 30 (OC6) & Related Modeling Improvements: Complete Phase I work focused on nonlinear hydrodynamic loading. Submit a summary paper to the TORQUE conference. CFD group will continue working on bichromatic wave cases, with hopefully some data to compare to from validation campaign. Begin development of specification for Phase II of OC6, focused on higher-fidelity modeling of soil-structure interaction. NREL will begin coupling of REDWIN soil/structure DLL to OpenFAST. New Validation Campaign: Complete the validation campaign at the OTRC facility, and get the data uploaded to the DAP. Review datasets and provide feedback to validation campaign. IEA Wind Task 29 (Aerodynamics) & Related Aero-Elastic V&V: Attend the IEA Task 29 meeting in Rome in February. IEA Wind Task 31 (WakeBench), Related Wind-Plant V&V, & Model Improvements: Finalize Wind Energy journal paper regarding development of FAST.Farm and validation of load predictions against HFM. Complete validation of FAST.Farm against met tower, LIDAR, and SCADA data measurements from Peetz Table wind farm. Publish the final Wind Energy journal paper on the three-way V&V collaborative involving A2e SWiFT data within WakeBench. Develop an improved near-wake correction model in FAST.Farm based on HFM actuator-disk simulations under high thrust conditions. Finalize the super controller implementation in FAST.Farm and complete the FAST.Farm user documentation. Update TurbSim and OpenFAST to support nonuniform spatial grids to improve computational efficiency for synthetic winds in FAST.Farm Sensitivity Analysis: Run TurbSim and FAST.Farm simulations for sensitivity of loads and power for turbines in small wind farm to variations in wind parameters. Upcoming Public Outreach/Industry Engagement: Amy Robertson and Jason Jonkman will attend the DeepWind conference in Trondheim, Norway on Jan. 15-17. Amy Robertson will attend meetings of the IECRE/TC88 Joint Working Forum on Model Validation. Publicly release FAST.Farm to the wind community for the first time. Initiate the follow-on extension to the DNV-GL JIP on “validation of turbulence models”. HPC Usage: No anticipated issues with allocation usage for Q2. fwta Q2 allocation: 115,000 isda Q2 allocation: Expect large usage for this quarter.