## Slide 1
Strategic Planning Aeroacoustics
DOE Wind and Water Power Program
2014

## Slide 2: Thrust Area Description and Vision
As more wind plants are developed and sited in proximity to residential areas, noise will grow as a major barrier to further wind energy development and efficient operation. The vision of the aeroacoustic thrust area is to bring clarity through new science, technology, education, to help industry answer critical questions, address public concerns about wind turbine noise, provide additional physics-based data that are required for regulators to establish sound policy, and enable development practical noise reduction methods and technology.
Improved understanding of wind plant noise may also directly lower the cost of wind energy. To comply with local regulations, wind plant owners often curtail their operation, reducing energy capture, and effectively increasing cost. Furthermore, potentially disruptive turbine technology designs, such as those with high tip speeds and downwind rotors, are often limited by noise constraints. Wind plant acoustic footprints can prevent developers from placing turbines in cost effective areas and extracting the maximum energy from a wind plant.
Additionally, there are many various noise regulations around the US and the world that create confusion and inconsistencies for policy makers and the public. Sound scientific data, analysis, and interpretation are needed to bring clarity. Misinformation is also prevalent, which adds to residents’ concerns and their resistance to wind farm development. The program will consider the comprehensive range of wind turbine sound characteristics including tonal propagation, amplitude modulation, low frequency noise, and infrasound.
The following proposal outlines the A2e Aeroacoustics thrust area research that, when completed, will provide a deeper insight into public annoyance, wind plant noise generation and propagation mechanisms, as well as mitigation strategies. Ultimately, such knowledge will be translated into design tools and control algorithms that will enable turbine designers and plant developers and owners to effectively address noise issues without sacrificing performance and reliability of the wind plant. Improved knowledge will also help advance regulations that could specifically address the unique aspects of wind plant noise and make them more agreeable to surrounding communities. Such breakthroughs are necessary to accelerate wind energy’s growth while reducing the ultimate cost of wind relative to other energy technologies.
[Please enter 2-3 concise paragraphs describing your thrust area and explaining its motivation. Where do you see this going? What can be accomplished by 2020? (If you need more space, please make a copy of this page, insert it directly after this page, and simply keep writing.)]
Aeroacoustics

## Slide 3: Thrust Area Primary Goals
The primary goals of the A2e Aeroacoustics thrust is a better understanding of the fundamental mechanisms of wind plant noise generation, propagation, and reception through scientific research and dissemination into public documentation that will benefit industry and communities alike. More specifically, goals include detailed observation and modeling of acoustic noise from wind plants, turbines and major components to provide additional physical insight of wind plant noise generation and propagation. The goals also include a better understanding of the unique aspects of wind turbine noise annoyance and identification of appropriate metrics and measurement methodologies that reflect the interaction between noise generation, propagation and perception. Lastly, the thrust area goals include an educational and outreach aspect aimed at the dissemination of the latest technical advances in noise modeling, noise mitigation and science concerning the impact of wind plant noise on people.
[Please enter 1-2 concise paragraphs describing the major goals of your Thrust Area. (If you need more space, please make a copy of this page, insert it directly after this page, and simply keep writing.)]
Aeroacoustics

## Slide 4: Desired Outcomes (please list in priority order)
Desired Outcome 1: Scientific basis for long-term advances in wind-plant noise prediction and reduction
  This outcome will provide a better physical understanding of the noise generation and propagation mechanisms that dictate wind plant noise, including turbine source noise, wind turbine interactions and far field propagation in a variety of environments.
  This outcome will also include technology transferred to the industry and public that will allow for more reliable and validated set of models to predict noise emissions from wind turbines and wind plants.
  3dB turbine source noise reduction relative to baseline rotor. This outcome will include recommendations for industry on how to design turbines at lower noise levels, relative to the A2e baseline turbine and current SOA in wind plant modeling. Any technologies to address this outcome must be demonstrated under relevant environmental conditions.
Desired Outcome 2: Standardized metrics and regulatory models for wind plant noise
  This outcome will encompass a better understanding of the characteristics of wind plant noise that are annoying to residents. This will enable the definition of metrics suitable for quantifying noise reduction and also guiding local regulations. The outcome will include development of best practices for noise measurement and simulations that can be used to standardize the compliance process.
  Regulatory models will be produced that will serve as a basis for a standardized methodology for determining community impacts. Models of source noise will largely be used by industry to develop technology, whereas models of atmospheric propagation and perception will be used to ensure regulation compliance.
  3 dB noise reduction at receptor using baseline rotor based on operational strategies of the wind plant. By better defining noise metrics and the regulatory tools required to predict that they are met, wind farms and turbine technology will be able to be operated to lower noise level margins .
Desired Outcome 3: Public information warehouse
  This outcome will be helpful for communities and industry alike by providing a reliable summary of the latest the latest technical advances in noise modeling, observation, and mitigation and science concerning the impact of wind plant noise on people produced both prior to and by this thrust area for a range of stakeholders.
Aeroacoustics

## Slide 5: Work Packages
Work Package 1: Community / human factor/ dose-response studies
  This work package is focused on gaining a better understanding of the human and community impacts of wind plant noise including what makes this noise source unique relative to other industrial noise sources. Once understanding is improved, new noise metrics will be developed that accurately reflect the annoyance of wind plant noise to inform improved regulations. The package also includes development of best practice guidelines for measurement and simulation of wind plant noise. The output from this work package will be disseminated through WP4 and use findings from WP2 and WP3 as inputs. It is not dependent on other work packages other than having representative recordings of wind plant noise used to study community response.
Work Package 2: Plant Level Noise and Propagation
  This work package encompasses experimental observations and simulation tool development of noise focused at the plant level. Much of this will involve better understanding of turbine noise interactions with the atmosphere, other turbines, local terrain, vegetation and residential structures. The package will also involve examination of wind plant operational strategies that may reduce noise. The output from this work package influences results in other work packages but can be implemented in parallel.
Work Package 3: Turbine Level Noise and Control
  This work package involves experimental observations and simulation tool development at the turbine level including turbine components. The work package will look at the fundamental understanding of noise generation and also explore possible noise mitigation technologies for the wind turbine design. The output from this work package influences results in other work packages but can be implemented in parallel.
Work Package 4: Public dissemination
  This work package involves the creation of a public information warehouse that will be used to summarize and distribute previous and ongoing research in the area wind plant noise. The work package will be dependent on output from other packages, though not exclusively and should commence immediately.
Aeroacoustics

## Slide 6: Work Package Alignment with Desired Outcomes
Work Package Name | Supported Outcome(s)
WP1: Community / human factor/ dose-response studies | Scientific basis for long-term advances in wind-plant noise prediction and reduction Through laboratory and community based studies researchers will improve the scientific basis for human annoyance from wind plant noise. Standardized metrics and regulatory models for wind plant noise Better understanding of human annoyance will lead to improved metrics , noise measurement and simulation practices and ultimately regulations specifically tailored to wind plant noise.
WP2: Plant Level Noise and Propagation | Scientific basis for long-term advances in wind-plant noise prediction and reduction Through joint field measurements and simulation tool development the scientific basis of noise from wind plant is propagated through and modified by the local environment. Standardized metrics and regulatory models for wind plant noise Improved propagation models can be used to improve models that are used to assess regulatory compliance.
WP3: Turbine Level Noise and Control | Scientific basis for long-term advances in wind-plant noise prediction and reduction Through joint observational and simulation efforts researchers will better understand the noise generation at the source and develop new noise mitigation technologies.
WP4: Public Dissemination | Public information warehouse The focus of this work package is the creation of a constantly updated website that summarizes relevant previous and ongoing research to address wind plant noise issues.
Aeroacoustics

## Slide 7: Work Package 1: Community / human factor/ dose-response studies
Aeroacoustics
Accelerated Scenario (Best Case) |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | 10/1/14 | 9/30/20 | 8.0
 | Literature review Laboratory dose-response studies Community dose-response studies Noise metric studies and development Best practice guidelines/standards for noise measurement and simulation |  | 
 | Deliverable 1 – Community dose-response curves Deliverable 2 – Wind energy specific noise metrics Deliverable 3 – Best practice guidelines for measurement and simulation |  | 
FY15 | Start | End | Budget ($M)
 | 10/1/14 | 9/30/15 | 1.0
 | Literature review Commence laboratory and community studies Summarize noise metrics within and outside wind industry |  | 
 | Deliverable 1 – Literature review including noise metrics Deliverable 2 – Study plans Deliverable 3 – Initial scientific publications |  | 
Accelerated work in this work package may provide a more solid basis on what aspects of wind plant noise are most annoying, which will help prioritize the research to be performed in WP2 and WP3. The program will consider the comprehensive range of wind turbine sound characteristics including tonal propagation, amplitude modulation, low frequency noise, and infrasound. Acceleration will also provide improved noise metrics at a faster pace that may have a potentially significant impacts on the overall wind industry and its regulation.
[Please provide a brief explanation as to why the Accelerated Scenario funding case may be justified. What can happen that otherwise might not be possible? How does this increase the odds of A2e being successful? What are the implications for linkages to other Work Packages?]

## Slide 8: Work Package 2: Plant Level Noise and Propagation
Aeroacoustics
Accelerated Scenario (Best Case) |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | 10/1/14 | 9/30/20 | 10.0
 | Literature review and baseline creation Extended field measurement campaign Industrial tool development for wind plant noise and propagation High fidelity noise and propagation model development including impacts of atmosphere, terrain, vegetation and residential structures Operational noise mitigation studies |  | 
 | Deliverable 1 – Experimental database Deliverable 2 – Industry simulation tools Deliverable 3 – High fidelity simulation tools Deliverable 4 – Operational strategies for 3 dB reduction at receiver |  | 
FY15 | Start | End | Budget ($M)
 | 10/1/14 | 9/30/15 | 2.0
 | Literature review and baseline creation Small scale experiments Large experimental campaign design Begin simulation tool development |  | 
 | Deliverable 1 – Baseline design Deliverable 2 – Experimental plan Deliverable 3 – Simulation tool roadmap |  | 
Accelerated work in this work package will improve the understanding of the interaction of wind turbine noise the local environment, terrain and residential structures. Such propagation models are the least technologically advanced in the wind industry and may have large potential impacts for wind plant siting, development and operation.
[Please provide a brief explanation as to why the Accelerated Scenario funding case may be justified. What can happen that otherwise might not be possible? How does this increase the odds of A2e being successful? What are the implications for linkages to other Work Packages?]

## Slide 9: Work Package 3: Turbine Level Noise and Control
Aeroacoustics
Accelerated Scenario (Best Case) |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | 10/1/14 | 9/30/20 | 10.0
 | Literature review and baseline creation Experimental campaigns for airfoils, blades, turbines and mitigation technologies Scaling studies for aeroacoustics High fidelity and industry simulation tool development Low noise rotor design and demonstration |  | 
 | Deliverable 1 – Open source databases and geometries Deliverable 2 – High fidelity simulation tool Deliverable 3 – Industry simulation tool Deliverable 4 – Low noise rotor design that is 3 dB below baseline |  | 
FY15 | Start | End | Budget ($M)
 | 10/1/14 | 9/30/15 | 1.5
 | Literature review and baseline creation Experimental campaign design Begin simulation tool development |  | 
 | Deliverable 1 – Baseline design Deliverable 2 – Experimental plan Deliverable 3 – Simulation tool roadmap |  | 
Acceleration of this work package will lead to a quicker understanding of noise at the turbine level, simulation tool development and ultimately low noise demonstration rotor. Design and deployment of low noise rotor is thought to be major cost in out years.
Better observations and simulation tools of turbine noise will lead to improved source models in both the community studies work package and plant level noise work package. Though parallel development is prefered.

## Slide 10: Work Package 4: Public Dissemination
Aeroacoustics
Accelerated Scenario (Best Case) |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | 10/1/14 | 9/30/20 | 3.0
 | Literature review including health impacts Website updates and support Recurring 6 month summaries of DOE and external research studies IEA Task on noise |  | 
 | Deliverable 1 - Website Deliverable 2 – Summary reports and guidelines |  | 
FY15 | Start | End | Budget ($M)
 | 10/1/14 | 9/30/15 | 0.5
 | Literature review and summary Website development and release Propose IEA task |  | 
 | Deliverable 1 – Website Deliverable 2 – Summary reports of previous scientific studies |  | 
This work package is the most easily accelerated for little additional cost and it begins as a summary of all previous research related to wind plant noise and creation of a continuously update public information website. The summary and website has the potential to be immediately impactful for the wind industry and will help dispel myths and misinformation that is currently impacting the wind industry. This work package links all of packages together as it will serve as a public conduit for the work done across the thrust area.

## Slide 11: Work Package 1: [Enter title here]
Aeroacoustics
[Please provide a brief explanation as to why the Most Likely Scenario funding levels are justified. What do we get at this funding level that we would not get with less funding? How does this increase the odds of A2e being successful? What are the implications for linkages to other Work Packages?]
Most Likely Scenario (Baseline Case) |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | xx/xx/xx | xx/xx/xx | XX
 | Major Activity 1 Major Activity 2 Major Activity 3 Major Activity 4 Major Activity N |  | 
 | Deliverable 1 Deliverable 2 Deliverable 3 Deliverable N |  | 
FY15 | Start | End | Budget ($M)
 | xx/xx/xx | xx/xx/xx | XX
 | Major Activity 1 Major Activity 2 Major Activity 3 Major Activity N |  | 
 | Deliverable 1 Deliverable 2 Deliverable N |  | 

## Slide 12: Work Package 1: Community / human factor/ dose-response studies
Aeroacoustics
Minimum To Get Started Scenario |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | 10/1/14 | 9/30/20 | 3.0
 | Literature review Laboratory dose-response studies Noise metric studies and development Best practice guidelines/standards for noise measurement and simulation |  | 
 | Deliverable 1 – Wind energy specific noise metrics Deliverable 2 – Best practice guidelines for measurement and simulation |  | 
FY15 | Start | End | Budget ($M)
 | 10/1/14 | 9/30/15 | 0.5
 | Literature review Planning of laboratory and community studies Summarize noise metrics within and outside wind industry |  | 
 | Deliverable 1 – Literature review including noise metrics Deliverable 2 – Study plans |  | 
Reduced funding for this work package will reduce the scale of the laboratory and eliminate community impact studies to a level at which the minimum scientific value can be extracted. There is potential that a lesser understanding of annoyance and correlation to wind plant noise will be gained.
[Please provide a brief explanation as to why the Minimum to Get Started Scenario is realistic and potentially sufficient. What is missing in this scenario that is present in the Most Likely Scenario? What types of future delays will result from this level of effort? Does this hamper the odds of A2e being successful? What are the implications for linkages to other Work Packages?]

## Slide 13: Work Package 2: Plant Level Noise and Propagation
Aeroacoustics
Minimum To Get Started Scenario |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | 10/1/14 | 9/30/20 | 3.0
 | Literature review and baseline creation Extended field measurement campaign Industrial tool development for wind plant noise and propagation Operational noise mitigation studies |  | 
 | Deliverable 1 – Experimental database Deliverable 2 – Industry simulation tools |  | 
FY15 | Start | End | Budget ($M)
 | 10/1/14 | 9/30/15 | 0.5
 | Literature review and baseline creation Experimental campaign design Begin simulation tool development |  | 
 | Deliverable 1 – Baseline design Deliverable 2 – Experimental plan Deliverable 3 – Simulation tool roadmap |  | 
Reduced work in this work package will focus on industry level simulation tool development and simple field campaigns to validate models. High fidelity modeling components will be eliminated. Effects of buildings on noise propagation will be based on existing studies with no additional research. Studies of improved operational strategies will be reduced.
[Please provide a brief explanation as to why the Accelerated Scenario funding case may be justified. What can happen that otherwise might not be possible? How does this increase the odds of A2e being successful? What are the implications for linkages to other Work Packages?]

## Slide 14: Work Package 3: Turbine Level Noise and Control
Aeroacoustics
Minimum To Get Started Scenario |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | 10/1/14 | 9/30/20 | 3.0
 | Literature review and baseline creation Experimental campaigns for airfoils, blades, turbines and mitigation technologies Scaling studies for aeroacoustics Industry simulation tool development |  | 
 | Deliverable 1 – Open source databases and geometries Deliverable 2 – Industry simulation tool |  | 
FY15 | Start | End | Budget ($M)
 | 10/1/14 | 9/30/15 | 0.5
 | Literature review and baseline creation Experimental campaign design Simulation tool initial development |  | 
 | Deliverable 1 – Baseline design Deliverable 2 – Experimental plan Deliverable 3 – Simulation tool roadmap |  | 
At a reduced level, this work package will focus more on industry level simulation tool development and smaller scale measurement campaigns. High fidelity modeling efforts will be eliminated. Fundamental understanding of noise will likely still be gained, but testing of mitigation technologies will be curtailed.
[Please provide a brief explanation as to why the Minimum to Get Started Scenario is realistic and potentially sufficient. What is missing in this scenario that is present in the Most Likely Scenario? What types of future delays will result from this level of effort? Does this hamper the odds of A2e being successful? What are the implications for linkages to other Work Packages?]

## Slide 15: Work Package 4: Public Dissemination
Aeroacoustics
Minimum To Get Started Scenario |  |  | 
Multi-year (FY15-FY20) | Start | End | Budget ($M)
 | 10/1/14 | 9/30/20 | 2.0
 | Literature review including health impacts Website updates and support Recurring 6 month summaries of DOE and external research studies |  | 
 | Deliverable 1 - Website Deliverable 2 – Summary reports |  | 
FY15 | Start | End | Budget ($M)
 | 10/1/14 | 9/30/15 | 0.4
 | Literature review and summary Website development and release |  | 
 | Deliverable 1 – Website Deliverable 2 – Summary reports of previous scientific studies |  | 
This work package is the inexpensive relative to its potential impact and it begins as a summary of all previous research related to wind plant noise and creation of a continuously update public information website. At a reduced funding level, the IEA Task focused on international collaboration will be eliminated and website publication will be delayed. The summary and website has the potential to be immediately impactful by helping dispel myths and misinformation that is currently impacting the wind industry. This work package links all of packages together as it will serve as a public conduit for the work done across the thrust area.
[Please provide a brief explanation as to why the Minimum to Get Started Scenario is realistic and potentially sufficient. What is missing in this scenario that is present in the Most Likely Scenario? What types of future delays will result from this level of effort? Does this hamper the odds of A2e being successful? What are the implications for linkages to other Work Packages?]

## Slide 16: Interaction with Other Thrust Areas
Thrust Area | Activities with Interaction and Crossover
High Fidelity Modeling | WP2: Wind farm simulations and parallel analytical work to distinguish the importance of the different potential contributors to amplitude modulation, including source rotation effects, source modulation effects, meteorological effects on propagation, turbine-turbine interaction, and turbine ABL interaction. WP2: High Fidelity models that are validated and open source and provide insight into the interaction of the atmospheric boundary layer with an entire wind farm, including meteorology and terrain (but not detailed turbine aeroacoustics) sufficient for providing the detailed inflow characteristics to individual turbines, and the propagation and combination of sound from those turbines to far field observers. WP3: High Fidelity models that are validated and open source that describes the aeroacoustic response of a complete turbine including unsteady wind-farm/weather/terrain specific inflow and noise mitigation technologies (incl. levels, tones, AM, LF & infrasound)
Experimental Measurement Campaigns | WP1: The development of experimental databases and practical prediction tools (designed for use by regulators, operators, etc) for determining the response of buildings to wind farm noise and the impact of acoustic insulation and other mitigation strategies, in particular for low frequency phenomena. WP1: Development of proper indoor & outdoor noise limits based on consistent noise metrics incl. levels, tones, AM LF & infrasound: identify which noise features most significantly impact community perception. Demonstrate these metrics using actual turbine and plant noise measurements from WP 2 and 3 WP2: Extended field measurement campaign that comprehensively describes the noise generated by a farm (better to measure several farms) including meteorology, terrain and wake effects (incl. levels, tones, AM, LF & infrasound) WP2: Development and validation of an open source engineering model for wind plant noise that describes the noise generated by a farm including meteorology, terrain and wake effects (incl. levels, tones, AM, LF & infrasound) WP2: Definition of low noise operation based instantaneous meteorological, terrain and wake effects WP3: Detailed aerodynamic and acoustic definition of the properties of a family of open, representative blade airfoils. WP3: An instrumented full turbine measurement campaign on baseline turbine (such as at the NREL or SWiFT facilities) to include steady and unsteady flow field definition (such as met tower, PIV, K-band radar, on-blade instrumentation) and acoustic characterization (including phased microphone array and 360 degree directivity) at the near and far field. WP3: Design of a low noise rotor as demonstrator WP3: Manufacturing and validation of low noise rotor by instrumented full turbine measurement campaign on baseline turbine with low noise rotor.
Aeroacoustics

## Slide 17: Work Package Interaction with Other Thrust Areas
Thrust Area | Activities with Interaction and Crossover
Integrated Wind Plant Control | WP2: Definition of low noise operation based instantaneous meteorological, terrain and wake effects
Data Archive and Portal | WP3: Development and dissemination of open databases for model validation WP4: A continuously updated website with summaries of the latest scientific social and technological studies, both inside and outside of DOE funding WP4: Links to A2e software development websites and experimental data
Integrated Wind Plant Design and Analysis | WP1: The development of experimental databases and practical prediction tools (designed for use by regulators, operators, etc) for determining the response of buildings to wind farm noise and the impact of acoustic insulation and other mitigation strategies, in particular for low frequency phenomena WP2: Development and validation of an open source engineering model for wind plant noise that describes the noise generated by a farm including meteorology, terrain and wake effects (incl. levels, tones, AM, LF & infrasound) WP2: Comparison of measurements and model with simple engineering models … elaborate best practices for simple engineering models for future wind farm noise propagation simulations
Financial Risk, Uncertainty, and Portfolio Analysis | Estimate current delayed or prevented wind plant construction and curtailment due to noise. Estimate effect on LCOE.
Aeroacoustics

## Slide 18: Appendix

## Slide 19: Planning Group Members
Planning Group Chair: Pat Moriarty, NREL
Planning Group Core Members:
  David Maniaci, Sandia
  Mark Bastasch, CH2MHill
  Kevin Kinzie, GE
  William Devenport, Virginia Tech
  Sanjiva Lele, Stanford
  Mark Shepherd, NASA Langley
Planning Group Industry Advisors
  Kevin Kinzie, GE
  Mark Bastasch, CH2MHill

## Slide 20: Draft Work Package Detail
Work Package 1: Community / human factor/ dose-response studies
  Literature overview
  Experimental dose-response studies incl. levels, tones, AM, LF & infrasound
  Community / human factor/ dose-response studies establishing the correlation basis for annoyance including documented terrain, meteorological, and wind-farm operating conditions, at substantially distinct sites (judged by terrain and population).
  The development of experimental databases and practical prediction tools (designed for use by regulators, operators, etc) for determining the response of buildings to wind farm noise and the impact of acoustic insulation and other mitigation strategies, in particular for low frequency phenomena: 5dB LF indoor noise reduction
  Development of proper indoor & outdoor noise limits based on consistent noise metrics incl. levels, tones, AM LF & infrasound: identify which noise features most significantly impact community perception. Demonstrate these metrics using actual turbine and plant noise measurements from WP 2 and 3
  Establish methods and procedures for consistently measuring wind plant noise for use by local regulators and consultants
Work Package 2: Plant Level Noise and Propagation
  Literature overview incl. overview on sophisticated and engineering propagation models
  Extended field measurement campaign that comprehensively describes the noise generated by a farm (better to measure several farms) including meteorology, terrain and wake effects (incl. levels, tones, AM, LF & infrasound)
  Development and validation of an open source engineering model for wind plant noise that describes the noise generated by a farm including meteorology, terrain and wake effects (incl. levels, tones, AM, LF & infrasound)
  Wind farm simulations and parallel analytical work to distinguish the importance of the different potential contributors to amplitude modulation, including source rotation effects, source modulation effects, meteorological effects on propagation, turbine-turbine interaction, and turbine ABL interaction.
  Comparison of measurements and model with simple engineering models … elaborate best practices for simple engineering models for future wind farm noise propagation simulations:
  High Fidelity models that are validated and open source and provide insight into the interaction of the atmospheric boundary layer with an entire wind farm, including meteorology and terrain (but not detailed turbine aeroacoustics) sufficient for providing the detailed inflow characteristics to individual turbines, and the propagation and combination of sound from those turbines to far field observers.
  Definition of low noise operation based instantaneous meteorological, terrain and wake effects: 3 dB noise reduction at receptor
Work Package 3: Turbine Level Noise and Control
  Literature overview
  Baseline creation -
  Development and dissemination of open databases for model validation that include:
    Detailed aerodynamic and acoustic definition of the properties of a family of open, representative blade airfoils.
    Definition of non-traditional sources (stall noise, leading edge noise) and source modifiers (unsteady inflow, pitch rate).
    An instrumented full turbine measurement campaign on baseline turbine (such as at the NREL or SWiFT facilities) to include steady and unsteady flow field definition (such as met tower, PIV, K-band radar, on-blade instrumentation) and acoustic characterization (including phased microphone array and 360 degree directivity) at the near and far field.
    Addresses noise s mitigation technology
  High Fidelity models that are validated and open source that describes the aeroacoustic response of a complete turbine including unsteady wind-farm/weather/terrain specific inflow and noise mitigation technologies (incl. levels, tones, AM, LF & infrasound) – overlapping with Aero HGM
  Design of a low noise rotor as demonstrator – overlap with experimental
  Scaling rules - airfoils, SWiFT, full scale, – what works? Overlaps with HFM and exp
  Manufacturing and validation of low noise rotor by instrumented full turbine measurement campaign on baseline turbine with low noise rotor: 3dB turbine source noise reduction
Work Package 4: Public dissemination
  A continuously updated website with summaries of the latest scientific social and technological studies, both inside and outside of DOE funding
  Links to A2e software development websites and experimental data
  Standards/guidelines for measurement and simulation of wind plant noise for developers, owners and regulating bodies
Aeroacoustics
GREEN = Defined Deliverable